## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Patrasayer | Bankura Division | Karajbani Piped Water Supply Scheme | SM/16702 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 23.46 | 0 | 0 | 0
2 | BANKURA | Patrasayer | Bankura Mechanical | Karajbani Piped Water Supply Scheme | SM/16702 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories for newly sunk TW No I and TW No II of Karajbani piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Patrashayar, Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000116/2024-2025 | 427/BMD | 27/06/2024 | 22/02/2025 | GOENKA ENTERPRISE | 51.06 | 8.49 | 16.63 | 21
3 | BANKURA | Patrasayer | Bankura Mechanical | Karajbani Piped Water Supply Scheme | SM/16702 | New | New sevice connection for Karajbani water supply scheme (SM/16702) at Patrasayer block under BMD PHE Dte. |  |  | BILL/01247/2024-2025 | BP-2024-25-322 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0 | 0
Total | [13 empty] | 78.19 | 8.49 | 10.86