## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Manik Bazar Piped Water Supply Scheme. | SM/16705 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 16.45 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Mechanical | Manik Bazar Piped Water Supply Scheme. | SM/16705 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Manikbazar piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 886/BMD | 04/05/2023 | 03/07/2023 | KINGKINI TRADERS | 37.08 | 19.35 | 52.18 | 45
3 | BANKURA | Sonamukhi | Bankura Mechanical | Manik Bazar Piped Water Supply Scheme. | SM/16705 | New | Manik Bazar Piped Water Supply Scheme. |  |  | BILL/01512/2023-2024 | BP-2023-24-114 | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.85 | 0 | 0 | 0
Total | [13 empty] | 61.38 | 19.35 | 31.52