## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Division | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 11.52 | 0 | 0 | 0
2 | BANKURA | Sonamukhi | Bankura Mechanical | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | New service connection for Dhansimla TW-1 |  |  | BILL/00027/2024-2025 | BP-2024-25-17 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.53 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Mechanical | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | Additional Quotation payment for diversion of HTOH line due to objection of local people for effecting of new connection at Dhansimla T/W-II |  |  | BILL/00729/2024-2025 | BP-2024-25-212 | 03/09/2024 | 03/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.95 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | Dhan Simla Piped Water Supply Scheme. |  |  | BILL/01516/2023-2024 | BP-2023-24-113 | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 13.04 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Mechanical | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | New service connection for Dhansimla T/W-II water supply under Bankura Mechanical Division PHE Dte. |  |  | BILL/00030/2024-2025 | BP-2024-25-18 | 24/07/2024 | 24/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.07 | 0 | 0 | 0
6 | BANKURA | Sonamukhi | Bankura Division | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DHANSIMLA PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 1196/BQA | 22/05/2023 | 01/01/2026 | SINGHA ENTERPRISE | 138.96 | 68.93 | 49.6 | 90
7 | BANKURA | Sonamukhi | Bankura Mechanical | Dhan Simla Piped Water Supply Scheme. | SM/16706 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Dhansimla piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer,Junior Engineer 1 | ORD/000423/2023-2024 | 1685/BMD | 27/07/2023 | 11/07/2026 | PRADIP KUMAR DHABAL | 37.28 | 17.48 | 46.87 | 46
Total | [13 empty] | 210.35 | 86.4 | 41.08