## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Khatra, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-5B) (Sl. No. 10) | Assistant Engineer |  | ORD/000971/2022-2023 | 188/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.87 | 3.82 | 98.66 | 0
2 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone-5B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 1126/BMD | 24/05/2023 | 23/06/2023 | SUTRADHAR TRADERS | 2.39 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000508/2023-2024 | 2356/BQA | 14/08/2023 | 01/04/2025 | M/S TARUN KUMAR PATRA | 564.3 | 0 | 0 | 85
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Construction of 5 mtr. x 5 mtr. size new Staff Room with allied Works for Mukutmanipur, Khatra & Ranibandh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000483/2023-2024 | 2393/BQA | 16/08/2023 | 25/11/2024 | MOHAMMAD HASAN KHAN | 8.64 | 6.43 | 74.45 | 90
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0.84 | 10 | 99
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukutmanipur, Khatra & Ranibandh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001033/2023-2024 | 3439/BQA | 15/12/2023 | 29/01/2024 | SOUMITRA KUMAR DAS | 19.54 | 15.12 | 77.36 | 90
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 134.7 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 23.5 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | Laying additional HDPE pipeline, supply of sluice valve, construction of valve chamber with all other allied works under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-V/B) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2025-2026 | 1313/BQA | 17/06/2025 | 17/10/2025 | M/S TARUN KUMAR PATRA | 51.93 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐V/B WATER SUPPLY SCHEME | SM/16935 | Augmentation | "Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Mukutmanipur, Khatra & Ranibundh (Zone- V/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) Near Kharban More & (2) Near Khatra Adibasi Mahavidyalaya" | Assistant Engineer |  | ORD/001965/2024-2025 | 685/BQA | 12/03/2025 | 11/05/2025 | M/S TARUN KUMAR PATRA | 15.12 | 0 | 0 | 0
Total | [13 empty] | 832.39 | 26.21 | 3.15