## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Acceptance cum Formal work order for the work of Internal & external Illumination and allied works for Zone 7B of Augmentation of Mukutmonipur, Khatra Ranibandh piped water supply scheme under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 1129/BMD | 24/05/2023 | 23/06/2023 | CHAKRABORTY MINING & ENGINEERING. | 2.39 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Work Order for Preparation of Detailed Project Report for Agumentation of Mukutmanipur-Khatra-Ranibandh Water Supply Scheme, Block : Ranibandh, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Zone-7B) (Sl. No. 13) | Assistant Engineer |  | ORD/000972/2022-2023 | 191/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.3 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 1.65 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Construction of Chlorine Room at OHR Site for Mukutmanipur, Khatra & Ranibandh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001314/2023-2024 | 921/BQA | 15/03/2024 | 13/06/2024 | SANDIP PATI | 4.63 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0 | 0 | 99
6 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000211/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 6.81 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone‐ VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/16936) |  |  | BILL/00661/2024-2025 |  | 09/08/2024 | 09/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 5.65 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone‐ VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( SM/16936) |  |  | BILL/01241/2024-2025 | BP-226/2024-25 | 13/08/2024 | 13/08/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 5.65 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF (MUKUTMANIPUR, KHATRA & RANIBUNDH) ZONE‐VII/B WATER SUPPLY SCHEME | SM/16936 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design) with 20 mtr staging height including foundation, pipeline connection and cost of pipes, specials etc. with allied worksfor Mukutmanipur, Khatra & Ranibundh (Zone- VII/B) Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000736/2023-2024 | 2736/BQA | 04/10/2023 | 28/09/2026 | PARAMESWAR CHOWDHURY | 227.44 | 0 | 0 | 45
Total | [13 empty] | 265.94 | 0 | 0