## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Work Order for Water supply arrangement at different School by laying pipeline and installation of stand post under Lurka Zone-A of Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Under Jal Swapna & Jal Jeevan Mission Programme) (Sl. No. 02) |  | Junior Engineer | ORD/001014/2021-2022 | 21/KSD | 10/02/2022 | 12/03/2022 | JAGABANDHU MONDAL | 4.66 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 2412/BQA | 18/08/2023 | 18/08/2023 | Resource Division | 27.58 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Supplying, laying, fitting & fixing of HDPE pipeline of Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000882/2023-2024 | 3010/BQA | 03/11/2023 | 01/02/2024 | ASHOK KUMAR DEY | 69.32 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Chaka (327), Poshda (328), Murachhara (329), Dheko (330), Chorkul (331) & Golor (332) mouzas under Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza - 6 Nos. Total Household- 1628 Nos. | Assistant Engineer | Junior Engineer | ORD/000081/2023-2024 | 1052/BQA | 02/05/2023 | 02/04/2025 | AMIYA KUMAR BIT | 116.73 | 0 | 0 | 55
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Laying additional HDPE pipeline, supply of sluice valve, construction of valve chamber with all other allied works of Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2025-2026 | 1311/BQA | 17/06/2025 | 02/01/2026 | M/S BANERJEE & BANERJEE | 20.83 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Laying additional HDPE pipeline under Augmentation of Mukutmanipur, Khatra & Ranibundh Water Supply Scheme (Zone-IV/B) under Jal Jeevan Mission programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000178/2025-2026 | 1314/BQA | 17/06/2025 | 16/08/2025 | GOUTAM BHATTACHARYYA | 30.64 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Patmauli (305), Junbani (306), Katapal (339), Pechhela (340), Tikarpara (359), Mohanpur (361), Nischintapur (362), Dumuror (363) & Gobarda (364) mouzas under Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza - 9 Nos. Total Household- 1411 Nos. | Assistant Engineer | Junior Engineer | ORD/000083/2023-2024 | 1054/BQA | 02/05/2023 | 29/09/2023 | SUBHADIP KOLEY | 104.71 | 0 | 0 | 50
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Baksi (333), Khayerbani (334), Jaynagar (335), Gopalpur (336), Phutiberya (337) & Bandarbani (338) mouzas under Lurka (Zone-VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph-I) at Block- Raipur, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza - 6 Nos. Total Household- 1439 Nos. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 1098/BQA | 10/05/2023 | 31/12/2024 | SUBHENDU SEKHAR GORAI | 114.46 | 0 | 0 | 40
9 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mouzas under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. | SM/16940 | Retrofitting | Work order for Laying, Fitting & fixing 100 mm MS collecting line from river bed tube well to CWR with allied works under Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2024-2025 | 1831/BQA | 12/07/2024 | 31/03/2025 | PRADIP CHAKRABORTY | 89.29 | 0 | 0 | 90
Total | [13 empty] | 578.22 | 0 | 0