## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Kotulpur | Bankura Mechanical | Adwaitabati Piped Water Supply Scheme | SM/16942 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I, TW No-II of Adwitabati Piped water supply scheme Block : Kotulpur under Bankura Mechanical Division, PHE Dte. Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 766/BMD | 24/04/2023 | 21/10/2023 | TAPAN KUMAR SARKAR | 46.96 | 26.82 | 57.11 | 58
2 | BANKURA | Kotulpur | Bankura Division | Adwaitabati Piped Water Supply Scheme | SM/16942 | New | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 93.07 | 0 | 0 | 0
3 | BANKURA | Kotulpur | Bankura Mechanical | Adwaitabati Piped Water Supply Scheme | SM/16942 | New | New service connection at P/H-II of Adwaitabati W/S scheme |  |  | BILL/00526/2024-2025 | BP-2024-25-146 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.12 | 0 | 0 | 0
4 | BANKURA | Kotulpur | Bankura Mechanical | Adwaitabati Piped Water Supply Scheme | SM/16942 | New | New service connection at P/H-I of Adwitabati W/S Scheme |  |  | BILL/00533/2024-2025 | BP-2024-25-147 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.69 | 0 | 0 | 0
5 | BANKURA | Kotulpur | Bankura Division | Adwaitabati Piped Water Supply Scheme | SM/16942 | New | Balanced ancillary works for Awditawbati Water Supply Scheme under Kotulpur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001973/2024-2025 | 688/BQA | 12/03/2025 | 11/05/2025 | M/S TARUN KUMAR PATRA | 87.5 | 0 | 0 | 0
Total | [13 empty] | 239.34 | 26.82 | 11.2