## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Basudebpur piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 657/BMD | 17/04/2023 | 14/10/2023 | RAJIB COMPANY | 40.25 | 19.17 | 47.61 | 48
2 | BANKURA | Sonamukhi | Bankura Division | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 125.93 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Division | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BASUDEBPUR PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2023-2024 | 2335/BQA | 14/08/2023 | 06/12/2024 | KHAN ENTERPRISE | 529.02 | 72.88 | 13.78 | 2
4 | BANKURA | Sonamukhi | Bankura Division | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | Instalation of scheme information board for 2 nos. sites of Basudebpur Piped Water Supply Scheme (SM/16944) & 3 nos. sites of Dhulai Piped Water Supply Scheme. (SM/18753) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001895/2024-2025 | 573/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.75 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Mechanical | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | New three phase service connection for Basudebpur TW-I water supply scheme of sonamukhi block under Bankura Mechanical Division P.H.E Dte.(SM/16944) |  |  | BILL/01180/2024-2025 | BP-2024-25-300 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0 | 0
6 | BANKURA | Sonamukhi | Bankura Mechanical | Basudebpur Piped Water Supply Scheme. | SM/16944 | New | New three phase Service Connection for Basudebpur TW2 Water supply scheme of sonamukhi block under Bankura Mechanical Division PHE DTE.(SM/16944) |  |  | BILL/01181/2024-2025 | BP-2024-25-301 | 09/12/2024 | 09/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.86 | 0 | 0 | 0
Total | [13 empty] | 704.95 | 92.05 | 13.06