## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | SM/16950 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.28 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | SM/16950 | Augmentation | payment to rail |  |  | BILL/00004/2023-2024 | Rail04 | 11/04/2023 | 11/04/2023 | SOUTH EASTERN RAILWAY | 0.98 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | SM/16950 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000219/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.28 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | SM/16950 | Augmentation | Proposal of i) Bankura Saltora Road from CH : 11.715 KM and CH: 14.20 KM permanent restoration of road for the purpose of Jack pushing and opened cut method and pipe laying along Bankura Saltora Road for works under Augmentation of Sarberia water supply scheme by PHE under Bankura HIGHWAY Division in the district of Bankura. |  |  | BILL/02131/2023-2024 | FHTC/12 | 13/12/2023 | 13/12/2023 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 78.25 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). | SM/16950 | Augmentation | Construction and Commissioning of Balance 'FHTC (Funtional House Hold Tap Connection) in mouzas of Augmentation of Sarberia Water Supply Schemes (Including Left Out BRGF Mouzas). Block - Chhatna, Dist.- Bankura under Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block : - Chhatna, Name of Zone - Sarberia (Zone - I & II), No. of Mouza :- 38 nos. (Barabakra, Khairkanali, Laxminarayanpur, Kantasol, Pinasgoria, Ghoramuli, Dubrajpur, Bamunkuli, Mandaspara, Chowghara, Panchpukhuria, Janardanpur, Jhagrapur, Bhalaidiha, Brajamohanpur, Dhengakend, Gharamora, Musibdihi, Lohagar, Benagoria, Kalpathar, Ghosergram, Chamkara, Basulibandh, Karra, Beliara, Hari bandi, Migra, Siuligarya, Sarberia, Pathardihi, Mujra Kundi, Jamdahari, Kamarkuli, Kuludihi, Gurpota, Kalaiberia & Banagram). Total House Hold - 50 nos. | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 803/BQA | 11/04/2023 | 01/01/2026 | MANAS DEY | 13.61 | 0 | 0 | 91
Total | [13 empty] | 93.41 | 0 | 0