## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | SM/16951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 79BQA | 06/01/2023 |  | Resource Division | 33.2 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | SM/16951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000069/2023-2024 | 2732/BQA | 03/10/2023 |  | Resource Division | 0.64 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | SM/16951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000220/2023-2024 | 193/BQA | 22/01/2024 |  | Resource Division | 0.64 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Surface Water based piped water supply scheme for Sanabad, Kargahir and adjoining mouzas (Phase - I). | SM/16951 | Augmentation | Augmentation of Surface water based piped water supply scheme for Sanabundh, Kargahir and Adjoining Mouzas (JJM Revision) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000506/2023-2024 | 2355/BQA | 14/08/2023 | 10/05/2024 | GOPAL CHANDRA CHOWDHURY | 102.5 | 0 | 0 | 29
Total | [13 empty] | 136.99 | 0 | 0