## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 2269/BQA | 01/08/2023 | 31/12/2026 | M/S TARUN KUMAR PATRA | 153.91 | 0 | 0 | 82
2 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Continuation for supply 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for official use of Deputy Superintendig Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/04/2023 to 30/09/2023 (183 Days). | Assistant Engineer | Junior Engineer | ORD/001175/2022-2023 | 287\BSD | 24/03/2023 | 23/09/2023 | TARUN KUMAR BHATTACHARYYA | 0.87 | 2.04 | 235.13 | 100
3 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.64 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000221/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.64 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Bankura ¿Saltora Road at Ch:20.300 km to Ch: 24.00 Km Permanent restoration of road for the purpose of laying of UPVC pipe along and across of Jhantipahari HighSchool-Chhatna Saltora Road 20.30 km to 24.00km ( Bankura-Saltora Road) in connection with Augmentation of Sub-Surface water basd water supply scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Highway Division in the district of Bankura. |  |  | BILL/00959/2024-2025 |  | 20/09/2024 | 20/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 11.42 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Bankura ¿Saltora Road at Ch:20.300 km to Ch: 24.00 Km Permanent restoration of road for the purpose of laying of UPVC pipe along and across of Jhantipahari HighSchool-Chhatna Saltora Road 20.30 km to 24.00km ( Bankura-Saltora Road) in connection with Augmentation of Sub-Surface water basd water supply scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Highway Division in the district of Bankura. |  |  | BILL/01243/2024-2025 | BP-314/2024-25 | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 11.42 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Jhantipahari-Kashipur Road from Ch: 0.060 km to 0.760 Km Permanent Restoration of Road for the purpose of 'laying of UPVC pipe along & across of Jhantipahari High School ¿Chhatna Saltora Road 20.30 km to 24.00 km ( Bankura­Saltora Road) in connection with Augmentation of Sub-Surface water based water supply, scheme for Jhantipahari to accommodate FHTC in Chhatna Block' under Bankura Highway Division in the district of Bankura. SL NO:-4 |  |  | BILL/00958/2024-2025 |  | 20/09/2024 | 20/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 63.73 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. (Phase - I). | SM/16952 | Augmentation | Jhantipahari-Kashipur Road from Ch: 0.060 km to 0.760 Km Permanent Restoration of Road for the purpose of 'laying of UPVC pipe along & across of Jhantipahari High School ¿Chhatna Saltora Road 20.30 km to 24.00 km ( Bankura­Saltora Road) in connection with Augmentation of Sub-Surface water based water supply, scheme for Jhantipahari to accommodate FHTC in Chhatna Block' under Bankura Highway Division in the district of Bankura. SL NO:-4 |  |  | BILL/01244/2024-2025 | BP-313/2024-25 | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 63.73 | 0 | 0 | 0
Total | [13 empty] | 306.37 | 2.04 | 0.67