## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Zone-II Ekteswar) | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 1200/BQA | 22/05/2023 | 02/01/2027 | SUBHANKAR BANERJEE | 155.66 | 106.87 | 68.65 | 92
2 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Supplying fitting fixing of different dia. CIDF Sluice Valve & fittings & Construction of valve chamber in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR and adjoining mouzas W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000266/2023-2024 | 515/BSD | 12/06/2023 | 27/06/2023 | MANOJ GHOSAL | 0.89 | 0.89 | 99.72 | 22
3 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.75 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001202/2023-2024 | 455/BQA | 08/02/2024 | 09/03/2024 | ROY CHOWDHURY ASSOCIATES | 2.31 | 0 | 0 | 100
5 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza)from Lalbaba Ashram towards House of Badal Mukherjee in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001501/2023-2024 | 40/BSD | 10/01/2024 | 20/01/2024 | SUBHANKAR BANERJEE | 1 | 0.96 | 96.89 | 10
6 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza) from House of Badal Mukherjee towards Chowmatha More in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001327/2023-2024 | 33/BSD | 08/01/2024 | 18/01/2024 | SUBHANKAR BANERJEE | 1 | 1 | 100 | 10
7 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza) from House of Kamarpara towards Lalbaba Ashram in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001502/2023-2024 | 41/BSD | 10/01/2024 | 20/01/2024 | SUBHANKAR BANERJEE | 0.99 | 0.99 | 100 | 10
8 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Laying of HDPE Pipe Line (to increase pressure of Bejogram Mouza)from house of Rabi Lohar towards Bejogram in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001503/2023-2024 | 42/BSD | 10/01/2024 | 20/01/2024 | SUBHANKAR BANERJEE | 0.8 | 0.76 | 95.1 | 10
9 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Laying Extra HDPE Pipe Line for creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001318/2023-2024 | 15/BSD | 03/01/2024 | 13/01/2024 | SUBHANKAR BANERJEE | 0.94 | 0.93 | 99.53 | 10
10 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Laying HDPE Pipe Line (to increase pressure of Bejogram Mouza) from Chowmatha More to House of Rabi Lohar in connection with Jal Jeevan Mission (JJM) for Augmentation of EKTESWAR & its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte.Block - Bankura - II, Name of OHR -Ekteswar (Z -II). No.of Mouza :- 07, Name of mouza:- Shyamdaspur, Bhadul, Bhutsahar, Bejgram, Garerbon, Sanabandh & Ekteswar (Part). | Assistant Engineer | Junior Engineer | ORD/001323/2023-2024 | 32/BSD | 08/01/2024 | 18/01/2024 | SUBHANKAR BANERJEE | 0.98 | 0.98 | 99.61 | 10
11 | BANKURA |  | Bankura Division | Augmentation Ekteswar (Zone- II) & its adjoining mouzas under Bankura - II Block Water Supply Scheme. | SM/16953 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000222/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.75 | 0 | 0 | 0
Total | [13 empty] | 170.08 | 113.38 | 66.67