## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of OLA & adjoining mouzas and for Augmentation of SUKLAI & adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Onda, Name of OHR - Direct Pumping. No.of Mouza :- 02, Name of mouza:- Ola & Suklai. | Assistant Engineer | Junior Engineer | ORD/000152/2023-2024 | 1352/BQA | 02/06/2023 | 01/08/2023 | MANORANJAN GHOSH | 7.68 | 7.32 | 95.39 | 55
2 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.22 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | sinking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of SUKLAI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2023-2024 | 1353/BQA | 02/06/2023 | 29/11/2023 | NAYAN BARDHAN | 12.93 | 10.89 | 84.22 | 95
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Ola and Suktai and its adjoining mouzas water supply scheme under onda block(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000542/2023-2024 | 1978/BMD | 28/08/2023 | 26/12/2023 | JAL PRAVAHIKA PVT LTD | 19.84 | 17.53 | 88.36 | 95
5 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000223/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.22 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of OLA & adjoining mouzas and for Augmentation works of SUKLAI & adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Onda, Name of OHR - Direct Pumping. No.of Mouza :- 02, Name of mouza:- Ola & Suklai. | Assistant Engineer | Junior Engineer | ORD/000151/2023-2024 | 1351/BQA | 02/06/2023 | 01/08/2023 | SUNIL KUMAR MANDAL | 11.58 | 4.72 | 40.78 | 77
7 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) of Suklai & adjoining mouzas and for Augmentation works of SUKLAI & adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 1849/BQA | 12/07/2024 | 26/08/2024 | GON ASSOCIATES | 14.7 | 0 | 0 | 20
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machinery with other electro mechanical accessories at Add T/W for Augmentation of Ola and Suklai and its adjoining mouzas water supply scheme under onda block(BRGF Phase I) under Bankura Mechanical Division, PHE Dte Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000118/2024-2025 | 429/BMD | 27/06/2024 | 20/10/2025 | INDRAJIT MITRA | 9.2 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for Ola and Suklai its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16954 | Augmentation | Construction of Boundary Wall at Suklai River site Pump House and Sinking of 300 x 200 mm dia Tube well 120 mtr.Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source under Augmentation of Suklai and adjoining mouzas W/S Scheme under ONDA Water Supply Scheme (BRGF PH-I project) under Bankura Sadar Sub-Division of Bankura Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000481/2024-2025 | 2970/BQA | 26/11/2024 | 24/08/2025 | NAYAN BARDHAN | 17.68 | 0 | 0 | 85
Total | [13 empty] | 100.04 | 40.47 | 40.45