## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.43 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00141/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kotalpukur ( Zone B) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000519/2023-2024 | 1884/BMD | 17/08/2023 | 15/12/2023 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.09 | 69.84 | 69
4 | BANKURA |  | Bankura Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.43 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Creation of Balance 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Kotalpukur (Zone- B) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000404/2023-2024 | 2089/BQA | 27/07/2023 | 01/01/2026 | MUNMUN UPADHYAY | 249.33 | 145.87 | 58.51 | 70
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for Augmentation works at OHR site under Kotalpukur (ZONE -B) and its Adjoing moujazs water supply scheme under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000374/2024-2025 | 1003/BMD | 24/09/2024 | 22/05/2025 | KINGKINI TRADERS | 9.12 | 0 | 0 | 25
7 | BANKURA |  | Bankura Division | Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16955 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Kotalpukur (Zone- B) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001174/2023-2024 | 427/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 2.46 | 0 | 0 | 100
Total | [13 empty] | 351.02 | 202.96 | 57.82