## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.32 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00161/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kanchanpur ( Zone C) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000521/2023-2024 | 1885/BMD | 17/08/2023 | 15/12/2023 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.06 | 69.81 | 69
4 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Construction of Low lift Pump House, Boundary Wall under Augmentation works for Kanchanpur (Zone- C) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 1863/BQA | 12/07/2024 | 10/10/2024 | SUBHADIP KOLE | 22.81 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.32 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2023-2024 | 2030/BQA | 24/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 300.97 | 210.32 | 69.88 | 80
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Kanchanpur (Zone-C) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 502/BMD | 09/07/2024 | 04/07/2025 | KINGKINI TRADERS | 23.07 | 0 | 0 | 25
8 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Continuation hiring of car equivalent to Motor cab & Maruti Omni (Standard) with Mass emission standard of BS- III purchased on or after 01/05/2008 with Diesel car on monthly basis having license for contract carriage permit for Regional Transport Authority for office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/03/2025 to 30/04/2025) (61 Days) | Assistant Engineer | Junior Engineer | ORD/002112/2024-2025 | 301/BSD | 28/02/2025 | 30/04/2025 | GOURANGA NANDI | 0.29 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Continuation engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from (01.03.2025 to 30.04.2025) (61 Days) | Assistant Engineer | Junior Engineer | ORD/002113/2024-2025 | 302/BSD | 28/02/2025 | 30/04/2025 | GOUTAM GHOSH | 0.29 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Continuation for supply 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for inspection of JJM works across Bankura district of Deputy Superintending Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/04/2025 to 30/09/2025 (183 Days). | Assistant Engineer |  | ORD/002028/2024-2025 | 370/BSD | 28/03/2025 | 27/09/2025 | TARUN KUMAR BHATTACHARYYA | 0.87 | 0 | 0 | 0
Total | [13 empty] | 437.67 | 267.38 | 61.09