## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.32 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00161/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kanchanpur ( Zone C) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000521/2023-2024 | 1885/BMD | 17/08/2023 | 15/12/2023 | M/S SAJAHAN CHOWDHURY | 81.74 | 57.06 | 69.81 | 69
4 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Construction of Low lift Pump House, Boundary Wall under Augmentation works for Kanchanpur (Zone- C) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 1863/BQA | 12/07/2024 | 10/10/2024 | SUBHADIP KOLE | 22.81 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000225/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.32 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Kanchanpur (Zone-C) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 502/BMD | 09/07/2024 | 04/07/2025 | KINGKINI TRADERS | 23.07 | 0 | 0 | 25
7 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Continuation hiring of car equivalent to Motor cab & Maruti Omni (Standard) with Mass emission standard of BS- III purchased on or after 01/05/2008 with Diesel car on monthly basis having license for contract carriage permit for Regional Transport Authority for office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E Dte. With effect from (01/03/2025 to 30/04/2025) (61 Days) | Assistant Engineer | Junior Engineer | ORD/002112/2024-2025 | 301/BSD | 28/02/2025 | 30/04/2025 | GOURANGA NANDI | 0.29 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Continuation engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from (01.03.2025 to 30.04.2025) (61 Days) | Assistant Engineer | Junior Engineer | ORD/002113/2024-2025 | 302/BSD | 28/02/2025 | 30/04/2025 | GOUTAM GHOSH | 0.29 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Kanchanpur (Zone- C) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001177/2023-2024 | 429/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 3.54 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Construction of Pump House with all allied works at Kanchanpur (Zone- C), OHR Site under Augmentation of Kanchanpur (Zone- C) Water Supply Scheme under Jal Jeevan Mission (JJM) under Bankura Sadar Sub- Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000188/2024-2025 | 1852/BQA | 12/07/2024 | 01/03/2025 | M/S ASHA ENGINEERING | 13.94 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- D) | Assistant Engineer | Junior Engineer | ORD/001286/2023-2024 | 10/BSD | 03/01/2024 | 13/01/2024 | SUBHADIP KOLE | 0.96 | 0.96 | 99.94 | 100
12 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/001283/2023-2024 | 08/BSD | 03/01/2024 | 13/01/2024 | SUBHADIP KOLE | 0.96 | 0.96 | 99.94 | 100
13 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/001284/2023-2024 | 09/BSD | 03/01/2024 | 13/01/2024 | SUBHADIP KOLE | 0.96 | 0.96 | 99.94 | 100
14 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/001282/2023-2024 | 07/BSD | 03/01/2024 | 13/01/2024 | SUBHADIP KOLE | 0.96 | 0.96 | 99.94 | 100
15 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- G) | Assistant Engineer | Junior Engineer | ORD/001499/2023-2024 | 36/BSD | 08/01/2024 | 18/01/2024 | SUBHADIP KOLE | 0.54 | 0.53 | 98.51 | 100
16 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- H) | Assistant Engineer | Junior Engineer | ORD/001500/2023-2024 | 37\BSD | 08/01/2024 | 18/01/2024 | SUBHADIP KOLE | 0.54 | 0.54 | 99.88 | 100
17 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- E) | Assistant Engineer | Junior Engineer | ORD/001497/2023-2024 | 34/BSD | 08/01/2024 | 18/01/2024 | SUBHADIP KOLE | 0.96 | 0.96 | 100 | 100
18 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Laying of 90mm (OD) HDPE pipeline from Nirsa More to Nirsa Metya Para for creation of Balance 'FHTC (Functional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Part- F) | Assistant Engineer | Junior Engineer | ORD/001498/2023-2024 | 35/BSD | 08/01/2024 | 18/01/2024 | SUBHADIP KOLE | 0.92 | 0.92 | 99.99 | 100
19 | BANKURA |  | Bankura Division | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000368/2023-2024 | 2030/BQA | 24/07/2023 | 08/04/2026 | PRINCE INDUTRIES (INDIA) | 300.97 | 210.32 | 69.88 | 80
20 | BANKURA |  | Bankura Mechanical | Augmentation works for Kanchanpur (Zone - C) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16956 | Augmentation | Load enhancement Service connection charge for Kanchanpur (zone-C) OHR site water supply scheme Barjora block under BMD,PHE Dte. (SM/16956) |  |  | BILL/02193/2025-2026 |  | 12/03/2026 | 12/03/2026 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.89 | 0 | 0 | 0
Total | [13 empty] | 465 | 274.19 | 58.97