## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16957 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kalayani (Zone-B) & Adjoining mouza water supply scheme under Onda Block (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. , Dist: Bankura | Assistant Engineer |  | ORD/000552/2023-2024 | 1988/BMD | 28/08/2023 | 26/12/2023 | R.N.S. TRADING | 48.56 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16957 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.48 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16957 | Augmentation | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of KALYANI and adjoining mouzas W/S Scheme (Zone - B) under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (FHTC-416 Nos.) | Assistant Engineer | Junior Engineer | ORD/000431/2023-2024 | 2010/BQA | 19/07/2023 | 31/03/2026 | M/S TARUN KUMAR PATRA | 164.5 | 68.3 | 41.52 | 54
4 | BANKURA |  | Bankura Division | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16957 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000226/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.48 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for KALYANI (Zone-B) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16957 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HL pumping machineries and other electromechanical accessories at CWPH for Augmentation of Kalyani Zone -B and adjoining mouzas water supply scheme (BRGF Ph-I) Block -Onda under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Estimator,Junior Engineer | ORD/001097/2023-2024 | 3072/BMD | 12/03/2024 | 02/03/2026 | P.K. ENGINEERING | 47.94 | 0 | 0 | 65
Total | [13 empty] | 263.97 | 68.3 | 25.88