## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16958 | Augmentation | Augmentation of KALYANI and adjoining mouzas W/S Scheme (Zone - A) under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000295/2023-2024 | 1913/BQA | 13/07/2023 | 01/07/2026 | GOUTAM BHOWMIK | 143.3 | 111.41 | 77.74 | 90
3 | BANKURA |  | Bankura Mechanical | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16958 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Kalayani (Zone-A) and Adjoining mouza water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block Onda , Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000609/2023-2024 | 2083/BMD | 12/09/2023 | 10/01/2024 | P.K. ENGINEERING | 71.94 | 59.66 | 82.92 | 60
4 | BANKURA |  | Bankura Division | Augmentation works for KALYANI (Zone-A) and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/16958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000227/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1 | 0 | 0 | 0
Total | [13 empty] | 217.24 | 171.06 | 78.75