## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | inking of 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) & Bypass pipe line arrangemet from tube well to inlet pipe of OHR at Saulia (Zone - G) OHR site under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Jal Jeevan Mission (JJM) and Jal Swapna Fund) | Assistant Engineer | Junior Engineer | ORD/000697/2023-2024 | 2655/BQA | 21/09/2023 | 05/11/2023 | SAMIRUDDIN KHAN | 11.39 | 8.24 | 72.35 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.82 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00160/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Saulia ( Zone-G) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000303/2023-2024 | 1406/BMD | 18/07/2023 | 16/09/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 81.3 | 61.78 | 75.99 | 75
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No- II at Tail End site of Augmentation works for Saulia (Zone-G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000314/2024-2025 | 855/BMD | 29/08/2024 | 27/12/2024 | M/S NABIN GOPAL SENGUPTA | 19.1 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Saulia (Zone-G) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000161/2024-2025 | 503/BMD | 09/07/2024 | 06/11/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 13.19 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000231/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.82 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Service connection charge for Saulia (Zone -G) water supply scheme at head works site Barjora block under BMD,PHE Dte.(SM/16960) |  |  | BILL/00348/2024-2025 | BP-2024-25-170 | 07/08/2024 | 07/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.51 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Construction of Platform of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Saulia (Zone - G) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2023-2024 | 2090/BQA | 27/07/2023 | 22/04/2024 | SIB SANKAR CHOWDHURY | 328.41 | 0 | 0 | 60
10 | BANKURA |  | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | Road Crossing work by verious dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Saulia (Zone- G) Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000082/2025-2026 | 1021/BQA | 25/04/2025 | 24/06/2025 | SIBSANKAR CHOWDHURY | 30.95 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation works for Saulia (Zone - G) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16960 | Augmentation | upport service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Saulia (Zone- G) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2023-2024 | 433/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 3.39 | 0 | 0 | 100
Total | [13 empty] | 495.9 | 70.02 | 14.12