## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Construction of Platfrom of Existing 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Joytunga (Zone - H) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, Name of OHR - Joytunga (Zone - H), No. of Mouza :- 17 nos., Name of mouza:- (Jorshal, Dhenga kend, Kushma, Golhati, Bonomadhavpur, Ladna, Mathana, Kodalia, Bandarkhola, Ramharipur, Katapesia, Kolaberia, Maitha Gopinathpur, Bara Bendya, Joytunga, Kostia & Khemua), No. of Household- 3372 nos. | Assistant Engineer | Junior Engineer | ORD/000395/2023-2024 | 2080/BQA | 27/07/2023 | 01/05/2026 | UNIVERSAL CONSTRUCTION | 210.96 | 96.5 | 45.74 | 50
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Joytunga ( Zone-H) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000529/2023-2024 | 1893/BMD | 17/08/2023 | 15/12/2023 | A.G.ENTERPRISE | 81.78 | 50.13 | 61.3 | 62
3 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.93 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00143/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Construction of High lift Pump House, Low Lift Pump House, Boundary Wall and Laying Distribution system under Augmentation works for Joytunga (Zone - H) under Bankura - I, II, Barjora Block Water Supply Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000070/2024-2025 | 1505/BQA | 18/06/2024 | 01/01/2026 | SAIKAT CHOWDHURY | 82.04 | 0 | 0 | 10
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for JOYTUNGA (Zone-H) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 504/BMD | 09/07/2024 | 06/11/2024 | A.G.ENTERPRISE | 13.16 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Joytunga (Zone- H) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001182/2023-2024 | 434/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 3.7 | 0 | 0 | 100
8 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000305/2024-2025 | 658/BSD | 10/06/2024 | 25/06/2024 | GOUTAM MUKHERJEE | 0.96 | 0.96 | 100 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000306/2024-2025 | 659/BSD | 10/06/2024 | 25/06/2024 | GOUTAM MUKHERJEE | 0.8 | 0.8 | 100 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- C) | Assistant Engineer | Junior Engineer | ORD/000307/2024-2025 | 660/BSD | 10/06/2024 | 25/06/2024 | DAUD ALI KHAN | 0.96 | 0.96 | 100 | 100
11 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Laying extra HDPE pipe line to increase pressure at Chandar, Jorshal, Babhor khola, Ladna, Mathana , Barobendia Mouzas in connection with Near Chandar Rising main Air valve along with all allied works of Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora. (PART- D) | Assistant Engineer | Junior Engineer | ORD/000308/2024-2025 | 661/BSD | 10/06/2024 | 25/06/2024 | DAUD ALI KHAN | 0.97 | 0.97 | 100 | 100
12 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.93 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | Sinking of 1 (One) no 300 X 200 mm dia Tube well 120 mtr. Deep by direct rotary rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Joytunga (Zone - H) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Location:- Mouza- Maithagopinathpur, J.L. No.- 315, LR Plot No.- 485/1184) | Assistant Engineer |  | ORD/000155/2025-2026 | 1299/BQA | 17/06/2025 | 01/08/2025 | UNIVERSAL CONSTRUCTION | 11.02 | 0 | 0 | 0
14 | BANKURA |  | Bankura Mechanical | Augmentation works for Joytunga (Zone - H) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16961 | Augmentation | New Service connection charge at Barabendya CWR Site under Joytunga (zone-H) Water supply scheme Barjora block under BMD,PHE Dte. (SM/16961) |  |  | BILL/01343/2024-2025 | BP-2024-25-344 | 29/01/2025 | 29/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.51 | 0 | 0 | 0
Total | [13 empty] | 417.2 | 150.32 | 36.03