## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.67 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00144/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Telibedia ( Zone-M) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000441/2023-2024 | 1770/BMD | 01/08/2023 | 30/09/2023 | WEST BENGAL ENGINEERING CO. | 81.8 | 0 | 0 | 59
4 | BANKURA |  | Bankura Mechanical | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Telebedia( Zone-M) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 507/BMD | 09/07/2024 | 01/01/2025 | CHAKRABORTY MINING & ENGINEERING. | 13.17 | 0 | 0 | 53
5 | BANKURA |  | Bankura Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿at Balarampur,panchbaga & krishnanagar mouzas ICDS Centre & house hold of TELEBEDIA (Zone - M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 666/BSD | 10/06/2024 | 01/09/2024 | SAMIRUDDIN KHAN | 0.94 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000237/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.67 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Augmentation of TELEBEDIA (Zone - M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000425/2023-2024 | 2008/BQA | 19/07/2023 | 14/04/2024 | MADHU SUDAN RAKSHIT | 176.55 | 0 | 0 | 83
8 | BANKURA |  | Bankura Division | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Construction of Staff Room cum chlorine room, Construction of High lift Pump House and Crossing of Road by Jack pushing method for Augmentation of TELEBEDIA (Zone - M) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/001126/2024-2025 | 2975/BQA | 26/11/2024 | 27/12/2025 | SUBHADIP KOLE | 62.16 | 0 | 0 | 80
9 | BANKURA |  | Bankura Mechanical | Augmentation works for TELEBEDIA (Zone- M) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16964 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Telebedia (Zone M) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000040/2025-2026 | 244/BMD | 14/05/2025 | 12/08/2025 | DAS ENTERPRISE | 27.33 | 0 | 0 | 0
Total | [13 empty] | 368.8 | 0 | 0