## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection)¿ in connection with Jal Jeevan Mission (JJM) for ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - II, Name of OHR -Arjunpur No.of Mouza :- 02 nos. Arjunpur & Bahadurpur. Total House Hold -16 nos. |  | Junior Engineer | ORD/000563/2022-2023 | 62/BSD | 24/01/2023 | 31/01/2023 | COSMIC CONSTRUCTION | 0.96 | 0.96 | 99.87 | 100
2 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.65 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00145/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Arjunpur (Zone-N) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 1465/BMD | 18/07/2023 | 16/09/2023 | DAS ENTERPRISE | 81.56 | 48.97 | 60.04 | 71
5 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000439/2023-2024 | 2273/BQA | 01/08/2023 | 04/03/2025 | PARAMESWAR CHOWDHURY | 228.56 | 60.36 | 26.41 | 24
6 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Sinking of 01 (one) no. DTH Tube Well and Construction of High lift Pump House under Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) | Assistant Engineer |  | ORD/000369/2024-2025 | 2348/BQA | 09/09/2024 | 09/10/2024 | PARAMESWAR CHOWDHURY | 21.08 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Arjunpur ( Zone-N) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000163/2024-2025 | 505/BMD | 09/07/2024 | 06/11/2024 | RAJIB COMPANY | 8.79 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Laying MS pipe line across culvert at near Khejurbedia village and construction of column & footing of ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001040/2023-2024 | 1143/BSD | 22/11/2023 | 07/12/2023 | SONIA ENTERPRISE | 0.97 | 0.96 | 99.56 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000239/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.65 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation works for ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16966 | Augmentation | Crossing of Road by Jack pushing method with( 300 mm dia MS casing pipe ( 8mm thick for casing) & 150 mm dia MS carrier pipe for Augmentation of ARJUNPUR (Zone - N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Location of Site:- Kadmaghati More & Near Arjunpur OHR site (NH-60 Road) | Assistant Engineer | Junior Engineer | ORD/001104/2024-2025 | 2973/BQA | 26/11/2024 | 24/02/2025 | PARAMESWAR CHOWDHURY | 14.96 | 0 | 0 | 50
Total | [13 empty] | 363.7 | 111.26 | 30.59