## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Augmentation of KENDBONI (Zone - P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura-II, Name of OHR -KENDBONI (Zone - P), No. of Mouza :-12 nos mousas (Karanjora, Lapuria, Ladna, Garakusum, Mankanali , Khiraijur,Kendboni, Kantaboni, Mamurjuri, Dhansimul,, Sonamui & Malindasi), No. of Household, No. of Household- 200 nos. under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000424/2023-2024 | 2007/BQA | 19/07/2023 | 01/01/2027 | ASHIS KUMAR SAMANTA | 209.18 | 146.97 | 70.26 | 65
2 | BANKURA |  | Bankura Mechanical | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Kendbani (Zone P) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000526/2023-2024 | 1890/BMD | 17/08/2023 | 17/12/2025 | EASTERN INDIA SALES & SERVICE | 81.78 | 49.86 | 60.97 | 56
3 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Design Making & Erection of Disply board using Logo and tag line of Jal Jeevan Mission to the place at Dhan Simul (07), Baikunthapur (15), Arjunpur (42), Bhedua Purusottompur (264) & Chhatarkanali (268) of Swajal Gram/Har Ghar Jal Villages for awarness generation among the pepole of Bankura Sadar Sub- Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001059/2023-2024 | 1175/BSD | 22/11/2023 | 07/12/2023 | TAPAS DEY | 0.69 | 0.68 | 97.77 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.54 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00147/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Construction of Pump House cum chlorine room and Sinking of 03 (Three) no. 200 mm X 165 mm dia.X 250 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for Augmentation of KENDBONI (Zone - P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000201/2024-2025 | 1889/BQA | 15/07/2024 | 01/10/2026 | ASHIS KUMAR SAMANTA | 18.8 | 3.07 | 16.34 | 63
7 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Kendboni (Zone- P) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001198/2023-2024 | 451/BQA | 08/02/2024 | 09/03/2024 | ROY CHOWDHURY ASSOCIATES | 1.85 | 0 | 0 | 100
8 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Construction of High lift Pump House including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of KENDBONI (Zone - P) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2024-2025 | 2345/BQA | 09/09/2024 | 02/06/2025 | GANGADHAR MONDAL | 31.19 | 0 | 0 | 80
9 | BANKURA |  | Bankura Division | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000242/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.54 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/01612/2023-2024 | BP-2023-24-139 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0 | 0
11 | BANKURA |  | Bankura Mechanical | Augmentation works for KENDBONI (Zone- P) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16968 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System at Kendboni (Zone-P) OHR under Bankura-I.II and Barjora Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000142/2025-2026 | 437/BMD | 10/06/2025 | 08/09/2025 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 26.41 | 0 | 0 | 0
Total | [13 empty] | 375.92 | 200.58 | 53.36