## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.71 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00148/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Augmentation of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000380/2023-2024 | 2041/BQA | 24/07/2023 | 27/12/2025 | PRADIP RAJAK | 383.03 | 133.87 | 34.95 | 51
4 | BANKURA |  | Bankura Mechanical | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Bonkati (Zone R) under Bankura -I ,II Borjora Block Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000524/2023-2024 | 1888/BMD | 17/08/2023 | 15/12/2023 | SUNRISE ENGINEERING CORPORATION | 81.75 | 52.37 | 64.06 | 64
5 | BANKURA |  | Bankura Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000244/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.71 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/01611/2023-2024 | BP-2023-24-137 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.75 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Bankati (Zone-R ) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000009/2025-2026 | 144/BMD | 30/04/2025 | 29/07/2025 | EASTERN INDIA SALES & SERVICE | 20.27 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Bonkati (Zone- R) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2023-2024 | 453/BQA | 08/02/2024 | 09/03/2024 | ROY CHOWDHURY ASSOCIATES | 1.7 | 0 | 0 | 100
9 | BANKURA |  | Bankura Division | Augmentation works for BONKATI (Zone- R) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16969 | Augmentation | Construction of Boundary wall and High lift Pump House at OHR Site under Augmentation of BANKATI (Zone - R) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) | Assistant Engineer | Junior Engineer | ORD/000351/2024-2025 | 2346/BQA | 09/09/2024 | 26/07/2025 | PRADIP PATRA | 31.2 | 0 | 0 | 100
Total | [13 empty] | 530.61 | 186.24 | 35.1