## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Soil Investigation work for construction of OHR (500 CUM CAPACITY) under Augmentation works for JAGDALLA (Zone- S2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2023-2024 | 3039/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.49 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.79 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00149/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Augmentation of JAGDALLA (Zone - S) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (FHTC NO- 500) | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 1917/BQA | 13/07/2023 | 01/07/2026 | GOUTAM BHOWMIK | 135.16 | 38.7 | 28.63 | 18
5 | BANKURA |  | Bankura Mechanical | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Jagadalla (Zone-S) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000315/2023-2024 | 1466/BMD | 18/07/2023 | 16/09/2023 | M.S. ENTERPRISE | 81.82 | 61.5 | 75.17 | 48
6 | BANKURA |  | Bankura Mechanical | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Jagdalla ( Zone-S) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000152/2024-2025 | 495/BMD | 09/07/2024 | 06/11/2024 | M/S DE ENGINEERING CONCERN | 8.8 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for JAGDALLA (Zone- S) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16970 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000246/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.79 | 0 | 0 | 0
Total | [13 empty] | 231.33 | 100.2 | 43.31