## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.36 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Augmentation of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. No. of House Hold :- 100 | Assistant Engineer | Junior Engineer | ORD/000748/2023-2024 | 2780/BQA | 09/10/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 71.41 | 15.99 | 22.4 | 20
3 | BANKURA |  | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Augmentation of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. No. of House Hold :- 100 | Assistant Engineer | Junior Engineer | ORD/000749/2023-2024 | 2781/BQA | 09/10/2023 | 05/07/2024 | ASOKE BHATTACHARYYA | 71.41 | 19.58 | 27.41 | 20
4 | BANKURA |  | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Barbed wire Fencing works at CHATURDIHI (Zone - U-2) OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of CHATURDIHI (Zone - U) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001480/2023-2024 | 208/BSD | 02/02/2024 | 12/02/2024 | M/S BANERJEE & BANERJEE | 0.69 | 0.69 | 99.99 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000247/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.36 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Load enhancement charges for CHATURDIHI OHR under Bankura -I,II & Borjora (BRGF Ph-I) water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00379/2024-2025 | BP-2024-25-81 | 10/06/2024 | 10/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.43 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Soil Investigation work for construction of OHR (700 CUM CAPACITY) under Augmentation works for CHATURDIHI (Zone- U2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2023-2024 | 3041/BQA | 06/11/2023 | 01/10/2025 | G.MITRA AND ASSOCIATES | 0.63 | 0 | 0 | 100
8 | BANKURA |  | Bankura Mechanical | Augmentation works for CHATURDIHI (Zone- U) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16971 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift and Low Lift pumping machineries and other electromechanical accessories for Augmentation works for CHATURDIHI (Zone U) under Bankura I, II and Barjora Block Water Supply Scheme (BRGF Ph I Project). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001039/2023-2024 | 2971/BMD | 29/02/2024 | 23/02/2025 | ORIENTAL ENGINEERING CO. | 97.69 | 0 | 0 | 53
Total | [13 empty] | 243.98 | 36.26 | 14.86