## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Creation of Balance 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharthol, No.of Mouza :- 18, Name of mouza:- Chhendua, Chamkara, Fengabasa, Amlatara, Purandihi, Kumidya, Penchaldihi, Siarbada, Deba, Andharthol, Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata , FHTC-100 Nos. | Assistant Engineer | Junior Engineer | ORD/000818/2022-2023 | 723/BQA | 30/03/2023 | 28/06/2023 | GOURANGA NANDI | 25.82 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Adarsole (Zone-V) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000320/2023-2024 | 1469/BMD | 18/07/2023 | 16/09/2023 | R.N.S. TRADING | 81.81 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.36 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00151/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares for Horizontal Split Cashing Centrifugal Pumping Machineries at Belboni IBS Block Bankura-II under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000457/2023-2024 | 1783/BMD | 01/08/2023 | 30/10/2023 | B T PROJECTS PRIVATE LIMITED | 99.61 | 98.15 | 98.53 | 98
6 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Barbed wire Fencing works at ANDHARTHOLE (Zone - V-2) OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001482/2023-2024 | 209/BSD | 02/02/2024 | 12/02/2024 | SANTI RANJAN MANDAL | 0.85 | 0.85 | 99.93 | 100
7 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000252/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.36 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Construction of Platfrom of Existing 'FHTC' (Funtional House Hold Tap Connection) in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I, Name of OHR - Andharthol, No.of Mouza :- 18, Name of mouza:- Chhendua, Chamkara, Fengabasa, Amlatara, Purandihi, Kumidya, Penchaldihi, Siarbada, Deba, Andharthol, Sutijor, Shyamdanga, Ramjibanpur, Sunukpahari, Jamboni, Dabar, Tariba teridi & Haru Malliker Bonkata | Assistant Engineer | Junior Engineer | ORD/000819/2022-2023 | 724/BQA | 30/03/2023 | 31/05/2025 | SUMITA UPADHYAY | 37.06 | 28.88 | 77.91 | 55
9 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Sinking of 3 nos of 200mm X 165mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of ANDHARTHOL (Zone - V) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 794/BQA | 11/04/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 12.94 | 0 | 0 | 85
10 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Soil Investigation work for construction of OHR (300 CUM CAPACITY) under ANDHARTHOL (Zone- V2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 3042/BQA | 06/11/2023 | 01/10/2025 | G.MITRA AND ASSOCIATES | 0.63 | 0 | 0 | 100
11 | BANKURA |  | Bankura Mechanical | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Andharthole (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 146/BMD | 30/04/2025 | 29/07/2025 | SWAPAN ENTERPRISE | 40.67 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Support service for design of pipe network under Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001206/2023-2024 | 459/BQA | 08/02/2024 | 09/03/2024 | ROY CHOWDHURY ASSOCIATES | 2.31 | 0 | 0 | 100
13 | BANKURA |  | Bankura Mechanical | Augmentation works for ANDHARTHOL (Zone- V) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/16972 | Augmentation | Acceptance cum Formal work order for the work of Supply delivery and fitting fixing of Pump spares of HSC pumps at Belboni IBS, under Bankura I ,II and Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase I) under Bankura Mechanical Division PHE Dte. Dist Bankura | Assistant Engineer | Junior Engineer | ORD/000127/2024-2025 | 433/BMD | 27/06/2024 | 22/02/2025 | RABINDRA NATH KHAN | 96.81 | 0 | 0 | 98
Total | [13 empty] | 400.74 | 127.87 | 31.91