## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 2.25 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Pakhanna & its adjoining mouzas water supply scheme Block Barjora under under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 1768/BMD | 01/08/2023 | 30/09/2023 | M/S NABIN GOPAL SENGUPTA | 72.97 | 55 | 75.37 | 74
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Ground Water Based Pakhanna (Manachar) Pipe Water Supply Scheme under Bankura Division, Block - Barjora, District - Bankura. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1402/BMD | 12/12/2024 | 11/04/2025 | SK ENTERPRISE | 30.4 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000254/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 2.25 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | WBSEDCL, Quotation Bill for new power connection at Purakanda Pump House augmentation work under Pakhanna water supply scheme (SM/03512) |  |  | BILL/00727/2024-2025 | BP-2024-25-211 | 03/09/2024 | 03/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.57 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electro-mechanical accessories for P/H No-I & II at Tail End site of Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000328/2024-2025 | 867/BMD | 29/08/2024 | 27/12/2024 | SK ENTERPRISE | 12.1 | 3.1 | 25.63 | 71
7 | BANKURA |  | Bankura Division | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Construction of Pump House, Boundary Wall at 3nos locations i.c. Pakhanna OHR Site, Gopalpur and Purokonda and Laying additional distribution system under Augmentation works for Pakhanna and its adjoining Mouzas Water Supply Scheme within Barjora Block. | Assistant Engineer | Junior Engineer | ORD/000372/2024-2025 | 2350/BQA | 09/09/2024 | 08/12/2024 | TAPAS KUMBHAKAR | 60.29 | 0 | 0 | 25
8 | BANKURA |  | Bankura Division | Augmentation works for Pakhanna & its adjoining mouzas Water Supply Scheme within Barjora Block. | SM/16973 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Pakhanna and its adjoining mouzas. under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001176/2023-2024 | 428/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 0.92 | 0 | 0 | 100
Total | [13 empty] | 181.75 | 58.1 | 31.97