## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 4 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). |  |  | BILL/00154/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electro mechanical accessories for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I)( Zone-IA) under Bankura Mechanical Division, PHED. | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 1780/BMD | 01/08/2023 | 29/11/2023 | SUNRISE ENGINEERING CORPORATION | 81.75 | 0 | 0 | 30
4 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of MCC cum PDB and other electromechanical accessories for source Augmentation works for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase I) (Zone IA) At Damodhar River Bank site under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001034/2023-2024 | 2966/BMD | 29/02/2024 | 27/08/2024 | TAPAN KUMAR SARKAR | 28.66 | 0 | 0 | 68
5 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End site for Augmentation work for Barjora water supply scheme (Left out mouzas of Barjora Block under BRGF Phase-I) (Zone-IA) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 519/BMD | 09/07/2024 | 06/11/2024 | SINHA ELECTRICALS | 11.28 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | FHTC (Functional House Hold Tap Connection') in SCHOOL, ICDS & House hold in connection with Jal Jeevan Mission (JJM) for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjor under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. (Zone- IA). No. of Mouza :- 01 nos., (Tikargram), No. of Household- 08 nos. | Assistant Engineer | Junior Engineer | ORD/001043/2023-2024 | 1165/BSD | 22/11/2023 | 07/12/2023 | SAMIRUDDIN KHAN | 0.92 | 0 | 0 | 100
7 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | UPVC Pipe line inter connection From Lagardanga to Tikargram village of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase- I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone- IA) | Assistant Engineer | Junior Engineer | ORD/001075/2023-2024 | 1163\BSD | 22/11/2023 | 04/06/2024 | AMIR UDDIN KHAN | 0.92 | 0 | 0 | 100
8 | BANKURA |  | Bankura Mechanical | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | WBSEDCL, Quotation Bill for new power connection at Sahebdanga Pump House augmentation work under Barjora (Left out Mouza) (zone-IA ) water supply scheme (SM/16974) |  |  | BILL/00723/2024-2025 | BP-2024-25-200 | 23/08/2024 | 23/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.63 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) Block - Barjora, | Assistant Engineer | Junior Engineer | ORD/000336/2023-2024 | 1960/BQA | 18/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 352.95 | 0 | 0 | 80
10 | BANKURA |  | Bankura Division | Augmentation works for BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) (Zone-IA). | SM/16974 | Augmentation | Construction of High lift Pump House,Switch Room & Toilet with sanitary & water supply arrangement including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of BARJORA Water Supply Scheme (Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-IA) | Assistant Engineer | Junior Engineer | ORD/000076/2025-2026 | 1015/BQA | 25/04/2025 | 01/04/2026 | SOUMITRA KUMAR DAS | 32.17 | 0 | 0 | 0
Total | [13 empty] | 519.28 | 0 | 0