## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division,of Bankura Division PHE Dte. Block - Saltora, Name of OHR - Saburbandh, No. of Mouza :- 01 no., Rajpura (Part), Total House Hold :-17 nos. | Assistant Engineer | Junior Engineer | ORD/000680/2023-2024 | 813/BSD | 10/08/2023 | 25/08/2023 | TAPAN KUMAR UPADHYAY | 0.86 | 0 | 0 | 70
2 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Construction of valve chamber at Rajpura, Keserkundi, Salbedia, Krishnapur mouza) of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000708/2023-2024 | 818/BSD | 10/08/2023 | 20/08/2023 | TAPAN KUMAR UPADHYAY | 0.84 | 0 | 0 | 86
3 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Construction of concrete to cover the pipeline from pump house to Keser Kundi for construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh under Saltora block of Saburbandh W/S Scheme under Bankura Sadar Sub- Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000723/2023-2024 | 824\BSD | 11/08/2023 | 26/08/2023 | M/S S.M ENTERPRISE | 0.95 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Division, PHE Dte. Block - Saltora, No. of Mouza :- 01 nos. Rajpura, Total House Hold :-35 nos. | Assistant Engineer | Junior Engineer | ORD/000674/2023-2024 | 811/BSD | 10/08/2023 | 25/08/2023 | TAPAN KUMAR UPADHYAY | 0.87 | 0 | 0 | 87
5 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Division, PHE Dte. Block - Saltora, No. of Mouza :- 1 no., kesarkundi, Total House Hold :-30 nos. | Assistant Engineer | Junior Engineer | ORD/000676/2023-2024 | 812/BSD | 10/08/2023 | 25/08/2023 | TAPAN KUMAR UPADHYAY | 0.93 | 0 | 0 | 80
6 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Dismentling & reconstruction of concrete at Iswada mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000718/2023-2024 | 821/BSD | 11/08/2023 | 21/08/2023 | SK FAZLUL ALAM | 0.96 | 0 | 0 | 85
7 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.7 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for Augmentation of Saburbandh & Adjoining Mouzas Water Supply Scheme. | Assistant Engineer |  | ORD/001368/2024-2025 | 3131/BQA | 19/12/2024 | 19/03/2025 | AMITAVA CHAKRABORTY | 58.46 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Concreting work of road restoration at Sirpura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. (Part- A) | Assistant Engineer | Junior Engineer | ORD/000721/2023-2024 | 822/BSD | 11/08/2023 | 26/08/2023 | SONU SINGH | 0.95 | 0 | 0 | 100
10 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Concreting work of road restoration at Sirpura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. (Part- B) | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 823/BSD | 11/08/2023 | 26/08/2023 | ABDUL AZID KHAN | 0.92 | 0 | 0 | 100
11 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Concreting work of road restoration at Sirpura mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Saburbandh W/S Scheme under Bankura sadar sub Division of Bankura Division PHE Dte. (Part- C) | Assistant Engineer | Junior Engineer | ORD/001045/2023-2024 | 1146/BSD | 22/11/2023 | 07/12/2023 | SOURASIS KARAK | 0.95 | 0 | 0 | 100
12 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000261/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.7 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Augmentation works for Saburbandh & its Adjoining Mouzas Water Supply Scheme. | SM/16975 | Augmentation | Augmentation of Saburbandh & Adjoining Mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000367/2023-2024 | 2029/BQA | 24/07/2023 | 01/01/2026 | PRINCE INDUTRIES (INDIA) | 158.22 | 0 | 0 | 100
Total | [13 empty] | 228.32 | 0 | 0