## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16976 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.51 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16976 | Augmentation | Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Jorehira (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, Total House Hold - 350 Nos. | Assistant Engineer | Junior Engineer | ORD/000689/2022-2023 | 590/BQA | 20/03/2023 | 01/04/2026 | MUNMUN UPADHYAY | 86.2 | 0 | 0 | 90
3 | BANKURA |  | Bankura Division | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16976 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Jorehira (Zone-B) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000849/2023-2024 | 2975/BQA | 31/10/2023 | 30/11/2023 | MEASURE LAND | 1.8 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16976 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000262/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.51 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for JOREHIRA (Zone - B) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16976 | Augmentation | Laying of balance distribution system of pipeline with allied works for Augmentation of Jorehira (Zone - B) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Jorehira, (for mugathole, Khoyerboni, Benagoria, Arajuri & chandra village) | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 1300/BQA | 17/06/2025 | 01/01/2026 | TARINI CHARAN UPADHYAY | 40.77 | 0 | 0 | 0
Total | [13 empty] | 135.78 | 0 | 0