## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16977 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.72 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16977 | Augmentation | Support service for detail surveying, cross checking of abailable LOP and taking level at the interval of 50 mtr. by using Survey Instrument like DGPS / Drone and detailed design of pipe line by using Watergems Software on the basis of population density for Augmentation works for Nabagram (Zone-K) under Saltora- Chhatna water Supply Scheme (BRGF Ph-I project) of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000848/2023-2024 | 2974/BQA | 31/10/2023 | 30/11/2023 | GEO SOLUTION | 2.08 | 1.47 | 70.9 | 100
3 | BANKURA |  | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16977 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.72 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16977 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Creation of Balance FHTC (Functional House Hold Tap Connection), construction of platform with allied works for Augmentation of Nabagram (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte.Block - Chhatna, Name of OHR - Nabagram , Total House Hold - 275 nos. | Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 673/BQA | 28/03/2023 | 01/01/2026 | MUNMUN UPADHYAY | 96.68 | 28.12 | 29.09 | 35
5 | BANKURA |  | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16977 | Augmentation | Construction of Guard Room & Toilet with sanitary & water supply arrangement including plinth protection, Ramp etc. according to departmental design & drawing for Augmentation of Nabagram (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF ph - I project)under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001407/2024-2025 | 49/BQA | 02/01/2025 | 02/04/2025 | LABIR MIRSHAD KHAN | 5.33 | 0 | 0 | 2
6 | BANKURA |  | Bankura Division | Augmentation works for Nabagram (Zone- K) under Saltora- Chhatna Water Supply Scheme (BRGF Ph - I Project). | SM/16977 | Augmentation | Crossing major PMGSY Road by different dia MS pipe by trench less Technologies i.e Jack Pushing method with MS Carrier pipe and all alled works near Metyala Village at Saluni-Kamalpur Road under Augmentation of Nabagram (Zone - K) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project) under Jal Jeevan Mission under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001396/2024-2025 | 43/BQA | 02/01/2025 | 16/02/2025 | MUNMUN UPADHYAY | 4.61 | 0 | 0 | 10
Total | [13 empty] | 112.15 | 29.6 | 26.39