## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Zone-C (Biradihi) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000813/2022-2023 | 720/BQA | 30/03/2023 | 28/06/2023 | MA KANKALI ENTERPRISE | 37.13 | 0 | 0 | 30
2 | BANKURA |  | Bankura Division | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 1.23 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | New service connection of Biradihi OHR zone-C Piped Water Supply Scheme at t/w-I ,Moshiara of Hirbandh block under BMD PHE Dte. |  |  | BILL/00537/2024-2025 | BP-2024-25-145 | 25/07/2024 | 25/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.49 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | Construction of Pump House at Tubewell site of Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001372/2024-2025 | 30/BQA | 02/01/2025 | 02/01/2026 | KABISH KUMAR GHOSH | 7.12 | 0 | 0 | 80
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories and providing spares of existing gaseous chlorination system for Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Bankura Mechanical Division, PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000140/2024-2025 | 483/BMD | 09/07/2024 | 01/03/2026 | TAPAN KUMAR SARKAR | 27.35 | 0 | 0 | 20
6 | BANKURA |  | Bankura Division | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | Sinking of 300 mm X 200 mm X 200 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe,Construction of Pump House & Boundary wall at Tubewell site for Lurka (Zone - VA) by retrofitting of Raipur Water Supply Scheme (BRGF Ph - I) at Block - Raipur, Dist - Bankura under Jal Jeevan Mission Programme. under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000185/2025-2026 | 1323/BQA | 17/06/2025 | 02/11/2025 | ASHOK KUMAR DEY | 31.13 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Biradihi (Zone- C) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16980 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Biradihi (Zone-C) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000195/2025-2026 | 641/BMD | 11/07/2025 | 09/10/2025 | ABHIJIT MUKHERJEE | 22.82 | 0 | 0 | 0
Total | [13 empty] | 127.28 | 0 | 0