## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation of Lachiapur (Zone-D) under Khatra-Hirbandh-Ranibandh water supply scheme (BRGF-Ph-I) under under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000608/2023-2024 | 2082/BMD | 12/09/2023 | 01/09/2025 | RABINDRA NATH KHAN | 61.4 | 0 | 0 | 30
2 | BANKURA |  | Bankura Division | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Sinking of 1 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of CWR and Construction & Commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in different mouzas of Augmentation works for Zone-D (Lachiapur) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 1912/BQA | 13/07/2023 | 28/01/2025 | EARTH MOVING (INDIA) | 133.76 | 98.43 | 73.59 | 25
3 | BANKURA |  | Bankura Division | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Laying HDPE pipeline from Nanda village to Pakuria village, in Saluipahari village in connection with Augmentation of Lachiapur (Zone- D) Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000330/2024-2025 | 2254/BQA | 28/08/2024 | 01/02/2025 | MANAS DEY | 15.23 | 0 | 0 | 80
4 | BANKURA |  | Bankura Division | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.39 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Lachiapur (Zone D) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000059/2025-2026 | 255/BMD | 14/05/2025 | 12/08/2025 | ORIENTAL ENGINEERING CO. | 29.05 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Sinking of 3 Nos. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine), Construction of 3 Nos. pump house at tubewell site and laying distribution pipeline of Zone-D (Lachiapur) in connection with Augmentation of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001764/2024-2025 | 495/BQA | 25/02/2025 | 09/09/2026 | SUBHADIP KOLE | 45.97 | 0 | 0 | 20
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Neutralization System, Flowmeter, Motorized Sulice valve with related allied works at Biradihi (Zone C ) under Khatra Hirbandh Ranibandh Water Supply Scheme under BMD PHE Dte. Dist Bankura. | Driller-in-Charge | Junior Engineer | ORD/000060/2025-2026 | 256/BMD | 14/05/2025 | 12/08/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 27.35 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation works for Lachiapur (Zone- D) under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/16984 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pump motor set other allied works at Lachiapur(Zone-D) OHR under Khatra-Hirbandh-Ranibandh Water Supply Scheme BMD, PHE Dte | Driller-in-Charge | Junior Engineer | ORD/000196/2025-2026 | 642/BMD | 11/07/2025 | 09/10/2025 | JAL PRAVAHIKA PVT LTD | 34 | 0 | 0 | 0
Total | [13 empty] | 350.15 | 98.43 | 28.11