## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation for Gouripur Water Supply Scheme. | SM/17120 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.43 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation for Gouripur Water Supply Scheme. | SM/17120 | Augmentation | Augmentation for Gouripur Water Supply Scheme. |  |  | BILL/00153/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation for Gouripur Water Supply Scheme. | SM/17120 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection) & Sinking of 01 (One) no. 200 mm X 165 mm dia.X 280 mtr. deep Rig bore Tube Well (by DTH Rig machine) with allied works for creation of source in connection with Jal Jeevan Mission (JJM) for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. at Block- Bankura-I, Dist.- Bankura. No. of Household- 120 nos | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 795/BQA | 11/04/2023 | 10/07/2023 | SAIKAT CHOWDHURY | 50.64 | 42.85 | 84.61 | 85
4 | BANKURA |  | Bankura Division | Augmentation for Gouripur Water Supply Scheme. | SM/17120 | Augmentation | Construction of Boundary Wall in connection with Jal Jeevan Mission (JJM) for for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte.(Length 90 Mtr) | Assistant Engineer | Junior Engineer | ORD/000465/2023-2024 | 2387/BQA | 14/08/2023 | 29/07/2025 | MUKHERJEE CONSTRUCTION | 14.97 | 8.07 | 53.9 | 95
5 | BANKURA |  | Bankura Division | Augmentation for Gouripur Water Supply Scheme. | SM/17120 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000266/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.43 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation for Gouripur Water Supply Scheme. | SM/17120 | Augmentation | Construction of 01 (One) no. Pump House (5.40 M X 3.6M) including sanitary arrangement & land development work in connection with Jal Jeevan Mission (JJM) for Augmentation of Gouripur W/S Scheme under Bankura Sadar Sub -Division of Bankura division P.H.E.Dte. at Block- Bankura-I, Dist.- Bankura | Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 886/BQA | 19/04/2023 | 01/04/2025 | ARIJIT GUHA | 8.25 | 6.74 | 81.74 | 100
Total | [13 empty] | 75.72 | 57.66 | 76.15