## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17123 | Augmentation | Sinking of 2 No. 200mm X 165 mm dia.X 240 mtr. deep Rig Bore Tube Well (by DTH Rig machine) to CWR with allied works, Construction of 50 Cum. Clear Water Reservoir, Pump House and Boundary Wall, Construction of Over Head Reservoir (100 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000507/2023-2024 | 2359/BQA | 14/08/2023 | 10/05/2024 | SUMITA UPADHYAY | 164.56 | 0 | 0 | 30
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17123 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Augmentation work for Banpukuria under Khatra- Hirbandh- Ranibandh water supply scheme Block- Ranibandh under Bankura Mechanical Division, P.H.E. Dte. | Driller-in-Charge | Junior Engineer | ORD/000732/2023-2024 | 2207/BMD | 21/11/2023 | 19/05/2024 | M/S BIPUL BANERJEE | 40.48 | 31.94 | 78.9 | 78
3 | BANKURA |  | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17123 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
4 | BANKURA |  | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000004/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 25.08 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17123 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 3.35 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Banpukuria under Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph - I) | SM/17123 | Augmentation | New service connection at 1st CWR site of Banpukuria Water supply scheme |  |  | BILL/01176/2024-2025 | BP-2024-25-299 | 04/12/2024 | 04/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.97 | 0 | 0 | 0
Total | [13 empty] | 243.62 | 31.94 | 13.11