## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Supply, creation of Sign board at 8 (Seven) nos i.e. Patrasayer Sub District Water Testing Laboratory, Sanabandh Sub District Water Testing Laboratory, Saltora Sub District Water Testing Laboratory, Taldangra Sub District Water Testing Laboratory, Gangajalghati Sub District Water Testing Laboratory and Bishnupur Sub District Water Testing Laboratory, Onda Sub District Water Testing Laboratory and Bankura -ll sab district water testing laboratory under Bankura Division. (Sl No- 01) | Assistant Engineer |  | ORD/000554/2023-2024 | 79/BK | 03/05/2023 | 03/06/2023 | ABHIRUP MALLA | 0.91 | 0 | 0 | 30
2 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Supply, creation of Sign board at 8 (Seven) nos i.e. Raipur Sub District Water Testing Laboratory, Sonamukhi Sub District Water Testing Laboratory, Simlapal Sub District Water Testing Laboratory, Hijaldiha vivekananda Seva Samity Sub District Water Testing Laboratory, Brajarajpur Tentulia Mahila & Sishu Kalyan Samity, Sarberia Sub District Water Testing Laboratory and Mukutmanipur WTP Site Sub District Water Testing Laboratory.Bankura District Water Testing Laboratory under Bankura Division. (Sl No.- 02) | Assistant Engineer |  | ORD/000555/2023-2024 | 80/BK | 03/05/2023 | 03/06/2023 | ABHIRUP MALLA | 0.91 | 0 | 0 | 20
3 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Continuation Work order for providing services for operation of 10 (ten) nos Laboratory w.e.f.01.05.2023 to 31.05.2023 under Bankura Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000775/2023-2024 | 1526/BQA | 16/06/2023 | 14/09/2023 | CLIFFORD FACILITY SERVICES PVT. LTD. | 1.1 | 0 | 0 | 80
4 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Enhancement of monthly remuneration of laboratory personnel working under Bankura Division, P.H.E.Dte. (Arrear payment for 3 Lab from 01.01.2023 to 30.06.2023, Bankura -II,Simlapal, Sonamukhi Sub- District Laboratary). | Assistant Engineer |  | ORD/001172/2022-2023 | 2464/BQA | 30/12/2022 | 30/06/2023 | CLIFFORD FACILITY SERVICES PVT. LTD. | 2.83 | 0 | 0 | 85
5 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Enhancement of monthly remuneration of laboratory personnel working under Bankura Division, P.H.E.Dte. (Arrear bill for 10 Labs from 01.01.2023 to 23.04.2023) | Assistant Engineer |  | ORD/001173/2022-2023 | 2465/BQA | 30/12/2022 | 30/04/2023 | CLIFFORD FACILITY SERVICES PVT. LTD. | 4.4 | 0 | 0 | 85
6 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 01.01.2024 to 30.06.2024 . | Assistant Engineer | Junior Engineer | ORD/001560/2023-2024 | 278/BK | 29/12/2023 | 28/06/2024 | CHANPA SINGHA | 0.86 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Bankura District Laboratory, Gangajalghati & Patrasayer Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001612/2023-2024 | 211\A\BK | 21/09/2023 | 21/09/2024 | TAPAS DEY | 0.09 | 0 | 0 | 95
8 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | WORK ORDER FOR TAX CONSULTANT FEES FOR THE FINANCIAL YEAR 2022-23 & 2023-24 FOR THE OFFICE OF THE ASSISTANT ENGINEER ,R.W.S BANKURA SUB DIVISION P.H.E. Dte. |  | Junior Engineer | ORD/001350/2023-2024 | 44/BK | 23/02/2024 | 01/03/2024 | ATANU PATRA | 0.06 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Day to day Operation & Maintenance for 14(Forteen) Nos. PHED Managed Laboratories under Bankura Division, P.H.E. Dte. w.e.f. 01.09.2023 to 30.06.2024. (for 10 months) | Assistant Engineer | Junior Engineer | ORD/000578/2023-2024 | 193/BK | 31/08/2023 | 30/06/2024 | TAPAS DEY | 3.33 | 0 | 0 | 95
10 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Day to day Operation & Maintenance for the different Laboratories under Bankura Division, P.H.E. Dte. (for 02 months) w.e.f. 01.07.2023 to 31.08.2023. (Sl No-02) | Assistant Engineer |  | ORD/001016/2023-2024 | 163\BK | 30/06/2023 | 31/08/2023 | TAPAS DEY | 0.51 | 0 | 0 | 97
11 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Day to day operation & Maintenance for the different Laboratories under Bankura Division , P.H.E. Dte. (for 02 months) w.e.f. 01.07.2023 to 31.08.2023. | Assistant Engineer |  | ORD/001015/2023-2024 | 164\BK | 30/06/2023 | 31/08/2023 | TAPAS DEY | 0.14 | 0 | 0 | 98
12 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Repairing & maintenance works of Bankura District laboratory and 13 (Thirteen) nos. Sub District Water Testing Laboratories under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001133/2023-2024 | 265\BK | 08/12/2023 | 08/01/2024 | TAPAS DEY | 0.97 | 0 | 0 | 100
13 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work Order for Shifting of different materials Like FTKs (Fe,FRC,Bacteria, pH, TDS,Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Ranibandh, Indus, Bankura-I, Bankura-II, Joypur & Taldangra B.M.O.H Office under Bankura District (Sl No.-02) |  | Junior Engineer | ORD/001311/2023-2024 | 09\A\BK | 10/01/2024 | 17/01/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 100
14 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Raipur, Hirbandh, Saltora, Bishnupur, Indpur & Onda B.M.O.H Office under Bankura District (Sl No.-03) |  | Junior Engineer | ORD/001315/2023-2024 | 11\BK | 11/01/2024 | 18/01/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 100
15 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/001594/2023-2024 | 79\A\BK | 15/03/2024 | 22/03/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 85
16 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Supervision and extend support to NABL recognized Water Quality Testing Sub District Laboratory i.e. Sanabandh sub district water testing Laboratory under The Executive Engineer Bankura Division, Public Health Engineering Directorate, Government of West Bengal by assigning team of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation for on-site surveillance by NABL for a period of month from the date of commencement. | Assistant Engineer | Junior Engineer | ORD/001583/2023-2024 | 285\\BK | 29/12/2023 | 29/02/2024 | DULAL MAJUMDER | 0.9 | 0 | 0 | 95
17 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Providing services for operation of 02 (Two) Nos. Sub-District Water Testing Laboratories w.e.f. 01.07.2024 to 31.12.2024 (06 Months) under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000318/2024-2025 | 1536/BQA | 21/06/2024 | 21/12/2024 | TAPAS DEY | 7.08 | 0 | 0 | 95
18 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Mukutmanipur WTP Laboratory, Sanabandh & Bankura-II Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001610/2023-2024 | 210/BK | 21/09/2023 | 21/09/2024 | TAPAS DEY | 0.09 | 0 | 0 | 95
19 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Raipur, Taldangra & Simlapal Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001611/2023-2024 | 211/BK | 21/09/2023 | 21/09/2024 | TAPAS DEY | 0.09 | 0 | 0 | 95
20 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Festival Bonus of 1(One) no District Laboratory & 02 (Two) nos Sub-District Laboratories i.e. Sanabandh, Sarberia, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 236/BK | 04/10/2024 | 24/10/2024 | TAPAS DEY | 0.79 | 0 | 0 | 95
21 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Day to day Operation & Maintenance for the Assistant Engineer,R.W.S.Bankura Sub-Division office building and office premises under Bankura Division,P.H.E. Dte.(for 12 months)w.e.f. 01.05.2023 to 30.04.2024. | Assistant Engineer | Junior Engineer | ORD/001607/2023-2024 | 73/BK | 28/04/2023 | 28/04/2024 | GANESH ROY | 0.97 | 0 | 0 | 98
22 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Saltora & Sarberia Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001614/2023-2024 | 222\A\BK | 04/10/2023 | 04/10/2024 | TAPAS DEY | 0.06 | 0 | 0 | 96
23 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Installation of annual Internet Prepaid recharge of Bishnupur, Onda & Sonamukhi Sub-District Water Testing Laboratory under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001613/2023-2024 | 222/BK | 04/10/2023 | 04/10/2024 | TAPAS DEY | 0.09 | 0 | 0 | 95
24 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Festival Bonus of 04 (Four) nos. Sub-District Laboratories i.e. Saltora, Gangajalghati, Patrasayer, Bishnupur, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | Assistant Engineer | Junior Engineer | ORD/000409/2024-2025 | 237/BK | 04/10/2024 | 24/10/2024 | TAPAS DEY | 0.94 | 0 | 0 | 95
25 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Festival Bonus of 04 (Four) nos Sub-District Laboratories i.e. Onda, Raipur, Taldangra, Indpur, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | Assistant Engineer | Junior Engineer | ORD/000410/2024-2025 | 238/BK | 04/10/2024 | 24/10/2024 | TAPAS DEY | 0.94 | 0 | 0 | 95
26 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer , R.W.S Bankura Sub-Division P.H.E. Dte. to Sarenga, Patrasayer, Barjora, Gangajalghati & Mejia B.M.O.H Office under Bankura District (Sl No.-01) |  | Junior Engineer | ORD/001309/2023-2024 | 09\BK | 10/01/2024 | 17/01/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 100
27 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Shifting of different materials Like FTKs (Fe, FRC, Bacteria, pH, TDS, Turbidity & Fluoride) including Training Manuals, Data Record Sheet Book & Bags for carrying kits from Office of The Assistant Engineer ,R.W.S Bankura Sub-Division P.H.E. Dte. to Kotulpur, Khatra, Simlapal, Chhatna & Sonamukhi B.M.O.H Office under Bankura District (Sl No.-04) |  | Junior Engineer | ORD/001316/2023-2024 | 11\A\BK | 11/01/2024 | 18/01/2024 | ABHIRUP MALLA | 0.09 | 0 | 0 | 100
28 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 22.07.2023 to 31.12.2023. |  |  | ORD/001263/2023-2024 | 166\BK | 13/07/2023 | 23/12/2023 | CHANPA SINGHA | 0.77 | 0 | 0 | 70
29 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Festival Bonus of 04 (Four) nos Sub-District Laboratories i.e. Simlapal, Bankura-II, Sonamukhi & Joypur, under Bankura Division, P.H.E.Dte.for the financial year 2023-24 | Assistant Engineer | Junior Engineer | ORD/000411/2024-2025 | 239/BK | 04/10/2024 | 24/10/2024 | TAPAS DEY | 0.94 | 0 | 0 | 95
30 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Providing services for operation of 02 (Two) Nos. Sub-District Water Testing Laboratories w.e.f. 01.04.2024 to 30.06.2024 (03 Months) under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001587/2023-2024 | 911/BQA | 14/03/2024 | 14/06/2024 | TAPAS DEY | 3.54 | 0 | 0 | 95
31 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001591/2023-2024 | 78\A\BK | 15/03/2024 | 22/03/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 90
32 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Continuation Work Order for Providing services for operation of 1(one) No.District Water Testing Laboratory & 12 ( Twelve) Nos. Sub-District Water Testing Laboratories w.e.f. 01.07.2024 to 30.09.2024(03 Months) under Bankura Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000200/2024-2025 | 1587/BQA | 26/06/2024 | 26/09/2024 | CLIFFORD FACILITY SERVICES PVT. LTD. | 23.43 | 0 | 0 | 95
33 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/001592/2023-2024 | 78\B\BK | 15/03/2024 | 22/03/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 85
34 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Shifting of laboratory machineries from existing N.G.O laboratory to new construct PHED managed laboratory under Bankura Division P.H.E. Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001593/2023-2024 | 79\BK | 15/03/2024 | 22/03/2024 | ABHIRUP MALLA | 0.1 | 0 | 0 | 85
35 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Payment of laboratory staff for the months December 2023 & January 2024 |  |  | BILL/02624/2023-2024 | FHTC/03 | 12/03/2024 | 12/03/2024 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.9 | 0 | 0 | 0
36 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | honorarium of lab personal |  |  | BILL/00304/2024-2025 | BP-143/2024-25 | 02/07/2024 | 02/07/2024 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.9 | 0 | 0 | 0
37 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Lab Maintenance charges & Administrative expenses |  |  | BILL/00305/2024-2025 | BP-144/2024-25 | 02/07/2024 | 02/07/2024 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.2 | 0 | 0 | 0
38 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Water testing laboratory of our samity (BTMSKS) for administrative expecses for the monthe december 2023 to January 2024 |  |  | BILL/02623/2023-2024 | FHTC/03 | 12/03/2024 | 12/03/2024 | BRAJARAJPUR TENTULIA MAHILA & SISU KALYAN SAMITY | 0.09 | 0 | 0 | 0
39 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Supply of 1 (one) No. Diesel/ LPG/ CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, R.W.S. Bankura Sub- Division, P.H.E. Dte. W.e.f. 01.07.2024 to 31.12.2024 . | Assistant Engineer | Junior Engineer | ORD/000224/2024-2025 | 157\BK | 28/06/2024 | 29/12/2024 | CHANPA SINGHA | 0.87 | 0 | 0 | 0
40 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | REPARING & MAINTENANCE WORKS OF 1(One) NO. DISTRICT WATER TESTING LABORATORY AND 13(Thirteen)NOs. SUB DISTRICT WATER TESTING LABORATORIES w.e.f. 01.04.2024 to 31.03.2025 UNDER BANKURA DIVISION P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000079/2024-2025 | 1499/BQA | 18/06/2024 | 02/08/2024 | TAPAS DEY | 4.82 | 0 | 0 | 95
41 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Continuation work order for day to day Operation & Maintenance for 14 (Forteen)Nos. PHED Managed Laboratories under Bankura Division P.H.E.Dte. w.e.f 01.10.2024 to 31.12.2024 | Assistant Engineer | Junior Engineer | ORD/000417/2024-2025 | 228/A/BK | 30/09/2024 | 31/12/2024 | TAPAS DEY | 0.81 | 0 | 0 | 98
42 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for day to day Operation & Maintenance for 02 (Two)Nos. New PHED Managed Laboratories under Bankura Division P.H.E.Dte. w.e.f 01.07.2024 to 30.09.2024 | Assistant Engineer | Junior Engineer | ORD/000395/2024-2025 | 156/BK | 28/06/2024 | 28/09/2024 | TAPAS DEY | 0.23 | 0 | 0 | 96
43 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Continuation work order for Day to day Operation & Maintenance for 14(Forteen) Nos. PHED Managed Laboratories under Bankura Division, P.H.E. Dte. w.e.f. 01.07.2024 to 30.09.2024. (for 03 months) | Assistant Engineer | Junior Engineer | ORD/000094/2024-2025 | 154/BK | 28/06/2024 | 28/09/2024 | TAPAS DEY | 0.81 | 0 | 0 | 98
44 | BANKURA |  | Bankura Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/17128 | Support-WQMSP | Work order for Electrification works at Taldangra Sub-District Water Testing Laboratory, Heating and Office room under Taldangra Block under Bankura R.W.S Sub-Division under Bankura Division P.H.E Dte.(Sl. no. 04) | Assistant Engineer | Junior Engineer | ORD/001533/2024-2025 | 278/BK | 27/12/2024 | 26/01/2025 | TAPAS DEY | 0.73 | 0 | 0 | 98
Total | [13 empty] | 67.89 | 0 | 0