## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Prakash Zone-A Water Supply Scheme | SM/17222 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR PRAKASH ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000342/2023-2024 | 1966/BQA | 18/07/2023 | 02/04/2025 | SIB SANKAR CHOWDHURY | 164.12 | 34.49 | 21.02 | 60
2 | BANKURA |  | Bankura Division | Augmentation of Prakash Zone-A Water Supply Scheme | SM/17222 | Augmentation | Sinking of 1 no Tubewell and Construction of Pump House for Augmentation of Prakash (Zone - A) Water Supply Scheme. | Assistant Engineer |  | ORD/001366/2024-2025 | 3130/BQA | 19/12/2024 | 19/03/2025 | ZAKIR HOSSIN MONDAL | 20.45 | 0 | 0 | 15
Total | [13 empty] | 184.57 | 34.49 | 18.69