## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Vishnupur | Bankura Division | Dwarika Pipe Water Supply Scheme | SM/17224 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 18.58 | 0 | 0 | 0
2 | BANKURA | Vishnupur | Bankura Division | Dwarika Pipe Water Supply Scheme | SM/17224 | New | Preparation of Detailed Project Report for Proposed ground water based Dwarika pipe water supply scheme, under Bankura Division Block : Bishnupur, District : Bankura under Jal Jeevan Mission Program under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001211/2023-2024 | 485/BQA | 09/02/2024 | 08/07/2024 | ROY CHOWDHURY ASSOCIATES | 3.09 | 3.09 | 99.99 | 90
3 | BANKURA | Vishnupur | Bankura Mechanical | Dwarika Pipe Water Supply Scheme | SM/17224 | New | Dwarika Pipe Water Supply Scheme |  |  | BILL/01610/2023-2024 | BP-2023-24-136 | 07/03/2024 | 07/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.76 | 0 | 0 | 0
4 | BANKURA | Vishnupur | Bankura Division | Dwarika Pipe Water Supply Scheme | SM/17224 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR DWARIKA PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2023-2024 | 2323/BQA | 14/08/2023 | 01/01/2026 | DEBAKI RANJAN SARKAR | 631.76 | 219.97 | 34.82 | 87
5 | BANKURA | Vishnupur | Bankura Mechanical | Dwarika Pipe Water Supply Scheme | SM/17224 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro mechanical accessories for proposed ground water based Dwarika piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Bishnupur Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/001082/2023-2024 | 3060/BMD | 12/03/2024 | 30/06/2025 | RAJIB COMPANY | 44.62 | 7.42 | 16.63 | 55
Total | [13 empty] | 706.82 | 230.49 | 32.61