## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Simlapal | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for proposed Sub surface water based Tilabani piped water supply scheme Block Simlapal under under Bankura Mechanical Division, P.H.E. Dte | Driller-in-Charge | Junior Engineer | ORD/000617/2023-2024 | 2089/BMD | 12/09/2023 | 01/09/2025 | M/S S.S. ENTERPRISE(MURSHIDABAD) | 38.3 | 0 | 0 | 60
2 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Sinking of 2 (Two) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well using MS "T" and Laying, Fitting & fixing 100 mm M.S. collecting line from river bed tube well to CWR with allied works, Construction of Clear Water Reservoir (100 Cum.), Pump House, Boundary Wall, Construction of Over Head Reservoir (250 Cum.) with ancillary works, Laying Rising Main, Distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Tilaboni pipe water supply scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000826/2023-2024 | 2952/BQA | 31/10/2023 | 01/04/2026 | RAISINHA INFRASTRUCTURE PVT. LTD. | 376.25 | 159.07 | 42.28 | 65
3 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Bankura Sadar Sub- Division & Khatra Sub- Division of Bankura Division, P.H.E. Dte. (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000861/2023-2024 | 2953/BQA | 31/10/2023 | 30/12/2023 | K S GROUP | 5.18 | 0 | 0 | 70
4 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Preparation of Detailed Project Report for Proposed sub surface water based Tilaboni pipe water supply scheme, under Bankura Division, Block : Simlapal, District : Bankura under Jal Jeevan Mission Program under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001077/2023-2024 | 3539/BQA | 29/12/2023 | 28/01/2024 | LEMNISCATE | 3.03 | 3.03 | 100 | 90
5 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 15.5 | 0 | 0 | 0
6 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 15.5 | 0 | 0 | 0
7 | BANKURA | Simlapal | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | New service connection at CWR site of Tilaboni Piped Water Supply Scheme Mouza-Jamda,Vill-Tilaboni GP- Lakshmisagar JL No-38, Plot no.-67 of Simlapal block under BMD PHE Dte. |  |  | BILL/00985/2024-2025 | BP-2024-25-244 | 21/10/2024 | 21/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.04 | 0 | 0 | 0
8 | BANKURA | Simlapal | Bankura Mechanical | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA |  |  | BILL/01658/2023-2024 | BP-2023-24-180 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.93 | 0 | 0 | 0
9 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Crossing of distribution pipeline accross Khatra-Simlapal road by adopting trench less technologies (e.g. Jack Pushing method etc.) for Proposed sub surface water based Tilaboni pipe water supply scheme under Jal Jeevan Mission programme of Khatra Sub-Division of Bankura Division, P.H.E. Dte. Location of site: (1) Near Jarisa Primary School | Assistant Engineer | Junior Engineer | ORD/000187/2025-2026 | 1325/BQA | 17/06/2025 | 01/08/2025 | PRADYUMNA KOLEY | 5.07 | 0 | 0 | 95
10 | BANKURA | Simlapal | Bankura Division | PROPOSED SUB SURFACE WATER BASED TILABONI PIPE WATER SUPPLY SCHEME, UNDER BANKURA DIVISION , BLOCK : SIMLAPAL, DISTRICT : BANKURA | SM/17227 | New | Work Order for Installation of scheme information board for 2 nos. site of Proposed sub surface water based Tilaboni pipe water supply scheme [SM/17227], 2 nos. site of Augmentation of Piped Water Supply Scheme for Lakshmisagar [SM/18424] and 2 nos. site of Augmentation of Water Supply Scheme for Baricha, Zone-A and its adjoining Mouzas under Simlapal water Supply Scheme (BRGF Ph-I) [SM/17295] within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001923/2024-2025 | 167\KSD | 07/03/2025 | 17/03/2025 | PRADYUMNA KOLEY | 0.9 | 0 | 0 | 90
Total | [13 empty] | 467.72 | 162.1 | 34.66