## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-B Water Supply Scheme | SM/17228 | Augmentation | Augmentation of Akui Zone-B Water Supply Scheme |  |  | BILL/00185/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-B Water Supply Scheme | SM/17228 | Augmentation | Augmentation of Akui Zone-B Water Supply Scheme |  |  | BILL/01625/2023-2024 | BP-2023-24-160 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.09 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-B Water Supply Scheme | SM/17228 | Augmentation | Load enhancement charges for AKUI ZONE B water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00439/2024-2025 | BP-2024-25-113 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.85 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Akui Zone-B Water Supply Scheme | SM/17228 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AKUI ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 1920/BQA | 13/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 186.44 | 87.56 | 46.96 | 80
5 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-B Water Supply Scheme | SM/17228 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Akui (Zone-B) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000359/2023-2024 | 1695/BMD | 28/07/2023 | 27/05/2025 | ABHIJIT MUKHERJEE | 74.38 | 46.82 | 62.94 | 36
6 | BANKURA |  | Bankura Mechanical | Augmentation of Akui Zone-B Water Supply Scheme | SM/17228 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and installation of Panel with Automatic Chlorinator and Stabilizer machineries along with other allied electro-mechanical works for newly sunk TW at Akui Zone B boosting TW site of Indus water supply scheme under B.M.D. PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2025-2026 | 152/BMD | 30/04/2025 | 25/01/2026 | SEN BROTHERS | 18.86 | 0 | 0 | 30
Total | [13 empty] | 284.62 | 134.37 | 47.21