## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Amrul Zone-A Water Supply Scheme | SM/17229 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Amrul (Zone-A) piped water supply scheme(BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Indus , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000362/2023-2024 | 1696/BMD | 28/07/2023 | 26/09/2023 | PRADIP KUMAR DHABAL | 54.01 | 0 | 0 | 53
2 | BANKURA |  | Bankura Mechanical | Augmentation of Amrul Zone-A Water Supply Scheme | SM/17229 | Augmentation | Augmentation of Amrul Zone-A Water Supply Scheme |  |  | BILL/00180/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Amrul Zone-A Water Supply Scheme | SM/17229 | Augmentation | Load enhancement charges for AMRUL ZONE A water supply scheme under B.M.D P.H.E Dte |  |  | BILL/00435/2024-2025 | BP-2024-25-112 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Amrul Zone-A Water Supply Scheme | SM/17229 | Augmentation | Augmentation of Amrul Zone-A Water Supply Scheme |  |  | BILL/01622/2023-2024 | BP-2023-24-159 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.2 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Amrul Zone-A Water Supply Scheme | SM/17229 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF AMRUL ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- INDAS, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000345/2023-2024 | 1969/BQA | 18/07/2023 | 01/04/2025 | S.N POLYMERS PVT LTD | 159.83 | 0 | 0 | 85
6 | BANKURA |  | Bankura Division | Augmentation of Amrul Zone-A Water Supply Scheme | SM/17229 | Augmentation | Construction of Pump House and Boundary Wall for Augmentation of Amrul (Zone-A) Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001380/2024-2025 | 17/BQA | 02/01/2025 | 02/04/2025 | KASTURI ROY | 12.97 | 0 | 0 | 90
Total | [13 empty] | 233.55 | 0 | 0