## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying Rising Main for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000767/2023-2024 | 2873/BQA | 11/10/2023 | 25/11/2023 | SONU SINGH | 5.02 | 0 | 0 | 0
2 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying Rising Mainfor sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000768/2023-2024 | 2874/BQA | 11/10/2023 | 25/11/2023 | DURGADAS SINGHA | 5.02 | 0 | 0 | 0
3 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 80.61 | 0 | 0 | 0
4 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 7.04 | 0 | 0 | 0
5 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 3467/BQA | 20/12/2023 | 20/12/2023 | Resource Division | 12.07 | 0 | 0 | 0
6 | BANKURA | Saltora | Bankura Mechanical | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. |  |  | BILL/00196/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2 | 0 | 0 | 0
7 | BANKURA | Saltora | Bankura Mechanical | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electro mechanical accessories for Proposed surface water based Pabra under Water Supply Scheme Block- Saltora under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000446/2023-2024 | 1774/BMD | 01/08/2023 | 30/09/2023 | ABHIJIT MUKHERJEE | 46.8 | 32.3 | 69.01 | 37
8 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Construction of Pump House for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000692/2023-2024 | 2638/BQA | 21/09/2023 | 20/12/2023 | MA USHA CONSTRUCTION CO. | 11.58 | 0 | 0 | 0
9 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying of distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 2872/BQA | 11/10/2023 | 21/08/2024 | TAPAN KUMAR UPADHYAY | 28.41 | 9.18 | 32.3 | 20
10 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying of distribution pipeline and Construction & commissioning of ?FHTC (Functional House Hold Tap Connection)? for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000765/2023-2024 | 2868/BQA | 11/10/2023 | 24/03/2024 | BEAUTY CHATTERJEE | 41.67 | 11.56 | 27.75 | 20
11 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying of distribution pipeline and Construction & commissioning of ?FHTC (Functional House Hold Tap Connection)? for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000766/2023-2024 | 2869/BQA | 11/10/2023 | 25/11/2023 | BIJOY KOLEY | 41.67 | 13.04 | 31.29 | 20
12 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying of distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000790/2023-2024 | 2870/BQA | 11/10/2023 | 25/11/2023 | TAPAS KUMBHAKAR | 28.41 | 10.74 | 37.78 | 20
13 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Construction of 200 Cum. OHR for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000827/2023-2024 | 2947/BQA | 30/10/2023 | 26/07/2024 | ANWESHA CONSTRUCTION | 78.68 | 0 | 0 | 1
14 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Construction of Boundary Wall with ancillary works at OHR site for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000860/2023-2024 | 2639/BQA | 21/09/2023 | 01/04/2026 | ASHIS PAL | 12.71 | 9.93 | 78.14 | 5
15 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Soil Investigation work for construction of OHR (200 CUM CAPACITY) under Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000893/2023-2024 | 3044/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.56 | 0 | 0 | 100
16 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Balance Work of Soil investigation work for construction of OHR (200 cum capacity) under proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District- Bankura under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001601/2023-2024 | 421/BSD | 18/03/2024 | 28/03/2024 | K S GROUP | 0.94 | 0.94 | 100 | 100
17 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Material Requisition To Resource Division |  |  | RTOR000267/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 7.04 | 0 | 0 | 0
18 | BANKURA | Saltora | Bankura Mechanical | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | New 3 phase service connection for Pabra w/s Scheme |  |  | BILL/00728/2024-2025 | BP-2024-25-210 | 03/09/2024 | 03/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.59 | 0 | 0 | 0
19 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Laying of distribution pipeline and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ for sub surface water based Pabra pipe water supply scheme under Bankura Division, P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000791/2023-2024 | 2871/BQA | 11/10/2023 | 01/07/2025 | JAGADISH BANERJEE | 28.41 | 9.01 | 31.73 | 21
20 | BANKURA | Saltora | Bankura Division | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Route Survey Preparation of DPR for piped water supply scheme for uncover mouzas of Ramjibanpur (JL No- 85), Pabra (86) & Niamatpur (JL No- 92) Block- Saltora under Jal Jeevan Misson (JJM) of Bankura Sadar Sub - Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000853/2023-2024 | 2979/BQA | 31/10/2023 | 30/11/2023 | LEMNISCATE | 2.75 | 0 | 0 | 100
21 | BANKURA | Saltora | Bankura Mechanical | Proposed sub surface water based Pabra pipe water supply scheme under Bankura Division, Block- Saltora, District: Bankura. | SM/17231 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation work of 06 nos OHR under Saltora-Chhatna Water scheme under Bankura Mechanical Division, PHE Dte. Block : Saltora , Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000020/2025-2026 | 155/BMD | 30/04/2025 | 29/07/2025 | M/S NABIN GOPAL SENGUPTA | 29.72 | 0 | 0 | 0
Total | [13 empty] | 475.73 | 96.7 | 20.33