## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 3.47 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00139/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of Boosting pumping machineries and other electromechanical accessories at Tail End for Augmentation work for Maliara (Zone-A) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000158/2024-2025 | 500/BMD | 09/07/2024 | 06/11/2024 | SUTRADHAR TRADERS | 13.17 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000269/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 3.47 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Maliara ( Zone-A) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1404/BMD | 18/07/2023 | 15/11/2025 | B T PROJECTS PRIVATE LIMITED | 82.62 | 51.28 | 62.07 | 73
6 | BANKURA |  | Bankura Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Augmentation of MALIARA (Zone - A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000509/2023-2024 | 2360/BQA | 14/08/2023 | 01/11/2025 | SWAPAN KUMAR UPADHYAY | 294.78 | 49.87 | 16.92 | 46
7 | BANKURA |  | Bankura Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Continuation for hiring car equivalewnt to Motor Cab & Maruti Omni (Standard) with Mass emission standard of BS-III purchased on or after 01/05/2008 with Diesel car on monthly basis having license for contract carriage permit for Regional Transport Authority for office of the Assistant Engineer ,Bankura Sadar Sub-Division , P.H.E Dte. with effect from (01/01/2024 to 30/06/2024) (Six Months) | Assistant Engineer | Junior Engineer | ORD/001219/2023-2024 | 3538/BQA | 29/12/2023 | 29/06/2024 | GOURANGA NANDI | 0.87 | 2.39 | 273.83 | 100
8 | BANKURA |  | Bankura Division | Augmentation works for MALIARA (Zone- A) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17234 | Augmentation | Construction of High lift Pump House, including plinth protection, Ramp etc of departmental design & drawing in connection with Jal Jeevan Mission (JJM) for Augmentation of MALIARA (Zone - A) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000347/2024-2025 | 2341/BQA | 09/09/2024 | 03/12/2025 | ASHOK KUMAR DEY | 17 | 0 | 0 | 0
Total | [13 empty] | 416.87 | 103.54 | 24.84