## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.82 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Augmentation of CHINGANI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2023-2024 | 1923/BQA | 13/07/2023 | 01/06/2025 | SABIR ALI KHAN | 126 | 61.82 | 49.06 | 86
3 | BANKURA |  | Bankura Mechanical | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chingani & Adjoining mouza water supply scheme (BRGF Phase-I) under Bankura Mechanical Division, PHE Dte. Block : Onda, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000551/2023-2024 | 1987/BMD | 28/08/2023 | 26/12/2023 | MITRA ENTERPRISE | 35.6 | 24.58 | 69.05 | 60
4 | BANKURA |  | Bankura Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000271/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.82 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). |  |  | BILL/01629/2023-2024 | BP-2023-24-157 | 19/03/2024 | 19/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.2 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of H/L and L/L Pumping machinery with other elector mechanical accessories for Augmentation of Chingani and Adjoining mouza water supply scheme at mouza Dhengasole under Bankura Mechanical Division, PHE Dte. Block Onda, Dist Bankura | Assistant Engineer | Estimator,Junior Engineer | ORD/000122/2024-2025 | 432/BMD | 27/06/2024 | 22/06/2025 | UNITED TRADERS | 40.96 | 0 | 0 | 70
7 | BANKURA |  | Bankura Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Construction of Boundary Wall at Chingani CWR Site in connection with Jal Jeevan Mission (JJM) for for Augmentation of CHINGANI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001376/2024-2025 | 55/BQA | 02/01/2025 | 01/04/2026 | PRABIR BARDHAN | 8.31 | 0 | 0 | 1
8 | BANKURA |  | Bankura Division | Augmentation works for Chingani and its adjoining Mouzas Water Supply Scheme under Onda Block (BRGF Ph - I Project). | SM/17235 | Augmentation | Support service for design of pipe network under Augmentation of CHINGANI and adjoining mouzas W/S Scheme under ONDA Water supply scheme (BRGF ph - I project) under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000383/2024-2025 | 2435/BQA | 25/09/2024 | 25/10/2024 | ROY CHOWDHURY ASSOCIATES | 2.53 | 0 | 0 | 100
Total | [13 empty] | 225.25 | 86.4 | 38.36