## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.03 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00142/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Augmentation of Talanjuri (Zone - F) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000290/2023-2024 | 1911/BQA | 13/07/2023 | 01/07/2026 | GOUTAM BHOWMIK | 150.33 | 0 | 0 | 64
4 | BANKURA |  | Bankura Mechanical | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Talanjuri (Zone-F) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000311/2023-2024 | 1410/BMD | 18/07/2023 | 16/09/2023 | DEBJYOTI BASU | 81.81 | 0 | 0 | 64
5 | BANKURA |  | Bankura Mechanical | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and fitting Fixing of Pump spares for HSC pump installed at water treatment plant and pumping station at Dejuri , Block Borjora, Dist- Bankura under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000460/2023-2024 | 1786/BMD | 01/08/2023 | 30/10/2023 | S.P. CONSTRUCTION | 70.44 | 0 | 0 | 95
6 | BANKURA |  | Bankura Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000272/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.03 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Acceptance cum Formal work order for the work of Supply, delivery and fitting Fixing of Pump spares for VT pump and Valves on delivery line installed at Intake (Raw water) pumping station near Durgapur Barrage Block Borjora, Dist- Bankura under Bankura -I ,II & Borjora Block Surface Water Based Piped Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division. | Assistant Engineer | Junior Engineer | ORD/000185/2023-2024 | 962/BMD | 19/05/2023 | 18/07/2023 | MAHADEV ENTERPRISE | 55.76 | 0 | 0 | 89
8 | BANKURA |  | Bankura Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Road Crossing work by 100 mm dia MS carrier pipe infront of Bandhkana More at Bahara Khuliya mouza by Jack pushing method, inetrconnection of MS carrier pipe with UPVC/HDPE pipeline including fabrication of MS pipe & allied works for Augmentation of Talanjuri (Zone- F) Water Supply Scheme under JJM under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000342/2025-2026 | 1803/BQA | 19/08/2025 | 03/10/2025 | PRADIP PATRA | 6.27 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation works for Talanjuri (Zone ¿ F) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17236 | Augmentation | Support service for detail surveying, cross checking of available LOP and taking level at the interval of 50 mtr. by using survey instrument like DGPS / Drone and detailed design of pipeline by using Watergems Software on the basis of population density for Augmentation works for Talanjuri (Zone- F) under Bankura- I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). under Bankura Sadar Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001180/2023-2024 | 432/BQA | 08/02/2024 | 09/03/2024 | LEMNISCATE | 1.23 | 0 | 0 | 100
Total | [13 empty] | 369.41 | 0 | 0