## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | Augmentation of Morar Zone-A Water Supply Scheme |  |  | BILL/00164/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | Quotation for new service connection at Morar Z-A TW-III Mouza Bankati.SM - 17237 |  |  | BILL/01141/2024-2025 | BP-2024-25-288 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.75 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | Quotation for new serrvice connection at Morar Z-A TW-I Mouza Chowgan.SM-17237 |  |  | BILL/01093/2024-2025 | BP-2024-25-251 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.52 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | Quotation for new service connection charges at Morar Z-A TW-II Mouza Morar JL -117 plot- 121/1313.SM/17237 |  |  | BILL/01143/2024-2025 | BP-2024-25-289 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.69 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-A piped water supply scheme (BRGF Ph-I) under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000385/2023-2024 | 1708/BMD | 28/07/2023 | 13/01/2026 | M.S. ENTERPRISE | 82.01 | 0 | 0 | 70
6 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF MORAR ZONE-A PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000387/2023-2024 | 2047/BQA | 24/07/2023 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 217.47 | 0 | 0 | 90
7 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-A Water Supply Scheme | SM/17237 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of CWPH pumping machineries and other electromechanical accessories for Augmentation of Marar Zone-A and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission progremme under Bankura Mechanical Division PHE Dte, Dist :Bankura. | Assistant Engineer | Junior Engineer | ORD/001079/2023-2024 | 3058/BMD | 12/03/2024 | 03/09/2025 | M/S NABIN GOPAL SENGUPTA | 54.11 | 0 | 0 | 40
Total | [13 empty] | 374.06 | 0 | 0