## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 1.23 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00138/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Mechanical | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories at tail end site for Augmentation work for Augmentation work for Sonadaha( Zone-Q) under Bankura -I ,II and Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000166/2024-2025 | 508/BMD | 09/07/2024 | 06/11/2024 | M/S BIPUL BANERJEE | 8.77 | 0 | 0 | 60
4 | BANKURA |  | Bankura Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Soil Investigation work for construction of OHR (300 CUM CAPACITY) under Augmentation of Sonadaha (Zone- Q) under Bankura- I, II & Barjora W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000885/2023-2024 | 3036/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.49 | 0 | 0 | 100
5 | BANKURA |  | Bankura Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 1.23 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Sonadaha (Zone-Q) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000525/2023-2024 | 1889/BMD | 17/08/2023 | 14/06/2026 | PREMNATH MITRA | 81.81 | 0 | 0 | 65
7 | BANKURA |  | Bankura Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Augmentation of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000821/2023-2024 | 2930/BQA | 26/10/2023 | 01/01/2026 | SHANTA COLIBRI (INDIA) PVT LTD | 320.93 | 0 | 0 | 32
8 | BANKURA |  | Bankura Division | Augmentation works for SONADAHA (Zone- Q) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17240 | Augmentation | Construction of Boundary wall, High lift Pump House, Laying Rising Main under Augmentation of SONADAHA (Zone - Q) under Bankura - I, II & Barjora Block W/S Scheme (BRGF Ph - I Project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001341/2024-2025 | 3180/BQA | 24/12/2024 | 24/03/2025 | JAGADISH BANERJEE | 43.62 | 0 | 0 | 70
Total | [13 empty] | 459.59 | 0 | 0