## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 2732/BQA | 03/10/2023 | 03/10/2023 | Resource Division | 0.54 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). |  |  | BILL/00150/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Barbed wire Fencing works at ANCHURI (Zone - T-2) OHR Site in connection with Jal Jeevan Mission (JJM) for Augmentation of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001481/2023-2024 | 207/BSD | 02/02/2024 | 12/02/2024 | SANTI RANJAN MANDAL | 0.85 | 0.85 | 99.93 | 100
4 | BANKURA |  | Bankura Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000276/2023-2024 | 193/BQA | 22/01/2024 | 22/01/2024 | Resource Division | 0.54 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation work for Achuri (Zone-T) under Bankura -I ,II & Borjora Block Water Supply Scheme (BRGF Phase-I) under Bankura Mechanical Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 1468/BMD | 18/07/2023 | 09/03/2025 | ABHIJIT MUKHERJEE | 81.82 | 57.08 | 69.76 | 76
6 | BANKURA |  | Bankura Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Augmentation of ANCHURI (Zone - T) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division | Assistant Engineer | Junior Engineer | ORD/000394/2023-2024 | 2054/BQA | 24/07/2023 | 01/07/2025 | SAIKAT CHOWDHURY | 86.91 | 30.42 | 35.01 | 26
7 | BANKURA |  | Bankura Division | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Soil Investigation work for construction of OHR (500 CUM CAPACITY) under Augmentation works for ANCHURI (Zone- T2) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project) under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2023-2024 | 3040/BQA | 06/11/2023 | 06/12/2023 | K S GROUP | 0.58 | 0 | 0 | 100
8 | BANKURA |  | Bankura Mechanical | Augmentation works for ANCHURI (Zone- T) under Bankura - I, II & Barjora Block Water Supply Scheme (BRGF Ph - I Project). | SM/17241 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical accessories for Augmentation works at OHR Anchuri (Zone-T ) under Bankura - I, II & Barjora Block Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000010/2025-2026 | 145/BMD | 30/04/2025 | 29/07/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 21.59 | 0 | 0 | 0
Total | [13 empty] | 194.32 | 88.35 | 45.47