## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Augmentation of Morar Zone-B Water Supply Scheme |  |  | BILL/00165/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
2 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of HSC pumping machineries with allied work for Augmentation of Marar Zone-B and adjoining mouzas water supply scheme (BRGF Ph I) at CWR site Gopalpur , Block Bishnupur under Jal Jeevan Mission programme under Bankura Mechanical Division PHE Dte, Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000267/2024-2025 | 775/BMD | 20/08/2024 | 18/12/2024 | M/S NABIN GOPAL SENGUPTA | 44.9 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Construction of Boundary Wall and Pump House for Augmentation of Morar (Zone-B) Piped Water Supply Scheme. | Assistant Engineer |  | ORD/001363/2024-2025 | 3125/BQA | 19/12/2024 | 19/03/2025 | TAPAS DEY | 12.93 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Quotation for new service connection at Marar Zone-B TW-II Mouza Agunkumari ,Block Bishnupur.SM/17243 |  |  | BILL/01094/2024-2025 | BP-2024-25-249 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.76 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Quotation for new service connection at Morar Z-B TW-III Mouza Belsulia.SM-17243 |  |  | BILL/01140/2024-2025 | BP-2024-25-286 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.33 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Quotation for new service connection at Morar Z-B TW-I Mouza Chandabila .Block Bishnupur SM-17243 |  |  | BILL/01144/2024-2025 | BP-2024-25-287 | 21/11/2024 | 21/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.23 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Marar Zone-B piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block Bishnupur , Dist Bankura. | Assistant Engineer | Junior Engineer | ORD/000390/2023-2024 | 1711/BMD | 28/07/2023 | 13/01/2026 | M.S. ENTERPRISE | 95.96 | 72.81 | 75.87 | 81
8 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR AUGMENTATION OF MORAR ZONE-B PIPED WATER SUPPLY SCHEME, BLOCK- BISHNUPUR, DIST- BANKURA UNDER JJM UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000375/2023-2024 | 2037/BQA | 24/07/2023 | 11/10/2025 | M/S D.PALIT & CO. | 159.64 | 90.12 | 56.45 | 80
9 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Additional sinking of 1 no 300mm X 200mm X 165m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe for Augmentation of Morar Zone-B of Bishnupur Block (JJM) under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer |  | ORD/000263/2025-2026 | 1541/BQA | 14/07/2025 | 12/09/2025 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.02 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Instalation of scheme information board for 2 nos. sites of Augmentation of Chuamasina Zone-B Water Supply Scheme (SM/17427), 2 nos. sites of Augmentation of Morar Zone-A Water Supply Scheme (SM/17237) & 1 no. sites of Augmentation of Morar Zone-B Water Supply Scheme (SM/17243) within Bishnupur Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001805/2024-2025 | 534/VSD | 27/09/2024 | 12/10/2024 | SANTANU GARAI | 0.75 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation of Morar Zone-B Water Supply Scheme. | SM/17243 | Augmentation | Renovation of RCC Elevated Over Head Reservoir of 550 cum capacity with staging height 20 m and other allied works Augmentation of Chakuparsole Zone-B & Morar Zone-B Water Supply Scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000416/2025-2026 | 1968/BQA | 15/09/2025 | 14/12/2025 | ASHIS PAL | 11.9 | 0 | 0 | 0
Total | [13 empty] | 365.93 | 162.92 | 44.52